## About
Erewash Borough Council Performance Dashboard
Click on the links below to navigate the dashboard
Home | About this dashboard
Summary
Delivery Plan
Welcome to Erewash Borough Council's Performance Dashboard. The dashboard reports on four main areas: 1. 'Delivery Plan'. These are high level actions/projects for strategic and operational priorities across our services for the 2024-26 financial years. They also drive and measure progress against the Corporate Strategy. There are sub-tabs for each priority against the Corporate Strategy. 2. 'Performance Indicators'. A suite of key performance indicators that measure performance across the Council's services and underpin the Corporate Strategy. Again, these are split by Corporate Strategy priority. 3. 'Financial Summary'. A summary of the latest financial position 4. 'Risks'. A summary of the latest position against the risks on the Strategic Risk Register. Navigate through the dashboard using the links on the left hand side.
Performance Indicators
Financial Summary
Risks
Click the image below to see the 2024-28 Corporate Strategy

## Summary
a
Summary
Reporting period
Welcome to the third release of the new performance framework. Below is an overall summary for Corporate Strategy Actions and Key Performance Indicators. Updates and outturns for each by corporate priority are available on the relevant pages in this dashboard.
Q4 2024-25
Home
| Summary | Corporate Strategy Actions
96% of Delivery Plan actions were on target or completed at the end of Quarter 4. There are no siginificant issues at this stage. For more information on the amber action and the action yet to start, see the individual Delivery Plan priorities.
Delivery Plan
| Performance Indicators |  | Red | 0 | 0%
|  |  | Amber | 2 | 4.167%
| Financial Summary |  | Green | 40 | 83.33%
|  |  | Completed | 6 | 12.5%
Risks
|  |  | Not started | 1
Key Performance Indicators
73% of all KPIs were on target at the end of Quarter 4, with another 16% within their tolerance level. There were 4 red indicators; for further information on these and all indicators, see the individual priority tabs.
|  |  | Red | 6 | 13.95%
|  |  | Amber | 6 | 13.95%
|  |  | Green | 31 | 72.09%
|  |  | Not started/annual | 0

## Delivery programme
Corporate Strategy Delivery Plan
Reporting period
Q4 2024-25 | We have developed a 4-year 'Delivery Plan' to both drive, and measure progress against our new Corporate Strategy. The actions within the plan have been split into Years 1 & 2 (2024/25 and 2025/26), and Years 3 & 4 (2026/27 and 2027/28). The plan is divided into the four priorities, and then by the objectives for each of those priorities: 1. Economy and Regeneration Promote regeneration Progress economic growth opportunities Improve housing supply 2. Supporting Communities Support residents with the cost of living Improve housing access and standards Improve quality of life 3. Sustainable Environment Deliver and respond to climate change Implement new waste management Look after the borough’s green spaces 4. A Modern Council Make best use of resources Ensure financial stability Utilise technology to transform service delivery Performance is reported quarterly, with a 'Red, Amber, Green' rating, to show whether the action is expected to be completed by its target date. A summary table for progress against each priority is available on each priority page, with overall progress against the plan noted on the 'Summary' page of this dashboard.
Home
Summary
Delivery Plan
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Performance Indicators
Financial Summary
Risks

## Priority 1
Economy and Regeneration Actions
Reporting period
Q4 2024-25
Summary All actions have commenced and are progressing to target, with the exception of 1.1b and c, which have been placed on hold. Quarter 1-3 updates are provided for reference. As the plan progresses, we will provide a summary of all previous updates, in addition to the latest position.
[5 empty] | Red | 0 | 0%
Home |  |  |  |  | Amber | 2 | 18.18%
[5 empty] | Green | 9 | 81.82%
Summary |  |  |  |  | Completed | 0 | 0%
Delivery Plan |  |  |  |  | Not started | 0
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Performance Indicators | Objective | Corporate Strat Ref | Action | Directorate | Service | Owner | RAG | Latest update | Previous updates
| Promote regeneration | 1.1a | Regeneration of Long Eaton High Street and creation of new managed workspace units at the Stable Block | Resources | Planning | Steve Birkinshaw | Green | Long Eaton High Street - Public consultation confirmed support for emerging scheme design, giving confidence to develop design further towards forumulation of Target Cost. Stable Block - project at advanced stage of construction. | Long Eaton High St - Design ongoing through Derbyshire County Council partners. Construction expected to be completed Summer/Autumn 2026. Stable Block - Project delayed owing to defective works identified on site undertaken by previous contractor, additional costs implications still to be determined. Long Eaton High Street - significant milestone reached with General Arrangement being signed off by the Highway Authority. Stable Block - project now progressing to revised timetable.
Financial Summary | Promote regeneration | 1.1b | Explore options for bringing empty commercial properties back into use in town centres | Resources | Planning | Steve Birkinshaw | Amber | S215 process put on hold pending launch of new property improvement grant in 2025/26. | Enforcement action underway to issue Section 215 (untidy property) improvement notices. Dual purpose of improving public realm and prompting owners to bring them back into active economic use.
| Promote regeneration | 1.1c | Assessment of car park need and development of a Car Park Strategy | Environmental & Community Services | Operational Services | Steve Birkinshaw | Amber | Council Executive progressing aspects of Ilkeston Car Park Strategy. Long Eaton Car Park Strategy on hold pending completion of Long Eaton High Street Town Deal project. | Assessment and draft Car Park Strategy completed. Next step is progress towards internal approval.
Risks | Progress economic growth opportunities | 1.2a | Review progress made in implementing Economic Development Strategy | Resources | Planning | Steve Birkinshaw | Green | Strategic Priorty 1: Town Centres - 16 empty properties brought back into use with assistance of SPF funded signage grant, Long Eaton High Street design progressed with Town Deal funding. Strategic Priorty 2: Rural Recreation - SPF funded Rural Erewash marketing campaign reaches 150,000 people and increases visitor numbers by 21%. Strategic Priort 3: Development and Business Growth - SPF grants support 19 retail and 11 manufacturing businesses directly, and through contract with Erewash Partnership provides advice to 436 businesses including 109 new busines start-ups creating 146 jobs. | Progress being made on all three strategic objectives. Strategic priority 1: Town Centres - 13 Empty Shop signage grants issued, to help bring vacant properties back into use. Strategic priorities 2: Rural Recreation - Rural Erewash Website and Marketing campaign launched. 150,000 people reached via social media and 17,000 visits to website. Strategic priority 3: Development and Business Growth - 10 Research and Development Grants issued, supporting 9 businesses. Town Centres - four additional shops supported back into use through signage grants, Town Deal and EMCCA Brownfield Land projects progressing. Rural Tourism promotion project awaiting evaluation. Erewash Partnership delivered further business advice, supporting the formation of 19 new businesses.
| Progress economic growth opportunities | 1.2b | Continue to support the development of warehousing and industrial premises at the 200 acre New Stanton Park | Resources | Planning | Steve Birkinshaw | Green | Plot 1 now fully permitted and under development for 5 industrial units. Discussions on development of Plot 3 highly advanced. | Planning approval granted for 5 warehouse units on Plot 1 at New Stanton Park. Discussions underway with developers on potential further applications . Planning approval granted for electric vehicle charging facility with drive through food and drink offer, which is expected to improve the appeal of New Stanton to potential industrial occupiers.
| Progress economic growth opportunities | 1.2c | Engage and survey local businesses to identify business needs and unlock barriers to growth through the EMCCA | Resources | Planning | Steve Birkinshaw | Green | New Stanton park development, provided early through the Core Strategy Review process, under development to provide for the identified need for new industrial premises. | Erewash Partnership undertaking a project which includes a survey of local business Erewash Partnership survey confirms local demand for new industrial premises, including starter units. EMCCA effectively lobbied to secure local spend of SPF monies over 2025-26.
| Progress economic growth opportunities | 1.2d | Promote entrepreneurial opportunities through SPF including research and development grants, retail signage and business grants | Resources | Planning | Steve Birkinshaw | Green | At the close of this year's SPF funding period, 19 new retail buisnesses had been supported bringing 16 vacant shop units into use, and 11 businesses provided research and development support inlcuding 6 who were new to research and development. In total these businesses received £137,527 of direct grant funding. | 13 Empty shops filled via signage grant (7 in Ilkeston, 6 in Long Eaton). 10 Research and Development Grants issued, supporting 9 businesses. £157,110 spent. Match funding from private sector- £82,092. A further 4 empty shop grants issued and a new round of research and development grant funding launched.
| Improve housing supply | 1.3a | Adopt Core Strategy subject to the results of the public examination and enable new housing development through the planning system | Resources | Planning | Steve Birkinshaw | Green | Core Strategy Review Amendment approved by Council on 27/03/2025. | The Planning Inspector issued a post hearing letter on 4 September 2024 with a set of requirements. The council has responded to confirm how it will meet these requirements over a six month period. The inspector will then consider whether the plan is ready for adoption.
| Improve housing supply | 1.3b | Develop a new Housing Strategy/approach and action plan to meet local housing need | Environmental & Community Services | Regulatory & Housing Services | Nick Thurstan | Green | Draft strategy objectives agreed with draft strategy development underway and expected in May. | Objectives drafted and action plan being developed in draft form for consideration at Homelessness and Supported Accommodation Board. Once agreed, there will be a period of internal and external consultation. Strategy objectives under consideration by Portfolio Holder and draft document development underway for consideration by senior officers and members.
| Improve housing supply | 1.3c | Consider options for bringing empty residential properties back into use engaging with partners | Environmental & Community Services | Regulatory & Housing Services | Nick Thurstan | Green | Replies to letter to landlords of empty homes being received and analysed. Quick solutions to the issues raised being identified and implemented. Findings to be discussed at the corporate Homelessness and Supported Accommodation Board on 3 June to consider options for the more complex issues. | A letter targeting owners of long-term empty homes has been drafted to gauge the level of involvement needed to tackle the 'low hanging fruit'. However, resources will need to be identified corporately to engage with landlords to make any significant impact on the many empty homes; this will be included in the draft housing strategy for consideration. Letter to owners of long-term empty homes approved and to be posted early January.
| Improve housing supply | 1.3d | With partners encourage and promote increasing the supply of affordable housing | Resources | Planning | Steve Birkinshaw | Green | Planning permission granted for 259 homes north of Spondon, including 26 Fisrt Homes (starter homes to buy) on site and a financial contribution of £5.5 million for affordable housing delivery elsewhere in the Borough. | Change in emphasis of Town Deal Galaxy Row Project will deliver affordable homes. Application underway to deliver affordable homes at the former Ilkeston Argos, funded by the EMCCA Brownfield housing fund. Currently preparing business case following success at Expression of Interest stage.

## Priority 2
Supporting Communities Actions
Reporting period
Q4 2024-25
Summary All actions are on target, with one completed. Quarter 1-3 updates are provided for reference. As the plan progresses, we will provide a summary of all previous updates, in addition to the latest position.
[5 empty] | Red | 0 | 0%
Home |  |  |  |  | Amber | 0 | 0%
[5 empty] | Green | 14 | 93.33%
Summary |  |  |  |  | Completed | 1 | 6.667%
Delivery Plan |  |  |  |  | Not started | 0
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Performance Indicators | Objective | Corporate Strat Ref | Action | Directorate | Service | Owner | RAG | Latest update | Previous updates
| Support residents with the cost of living | 2.1a | Be an active member of the Financial Inclusion Network, deliver the cost of living action plan with partners and promote access to available support and services | Resources | Revenues and Benefits | Lisa Black | Green | As per Quarter 3. The partnership with CAB to provide direct referral for Council Tax debtors has been approved and work is underway to incorporate this into the 3 year SLA EBC has with the CAB. Latest DCC Financial Inclusion Group (FIG) attended, new Money advise leaflet made available digitally and this will be made available on website. | Head of Revenues & Benefits is an active member of the regional financial inclusion group. We have also developed links with Citizens Advice Bureaux (CAB) to develop best practice in relation to debt collection and supporting households in cyclical debt. Led the development of the response to Household Support Fund 5 and established working relationships with Derbyshire County Council leads on HSF. Update the same as Q1. Regular and routine attendance at Derbyshire wide Financial Inclusion Group. Quarterly meetings with CAB and recent business case provided to look to develop a direct relationship for debt referral in to CAB. To be progressed in line with a review of Council Tax debt recovery procedures. Worked in partnership with CAB to promote take up of Pension Credit, with a direct mailing to over 1200 pensioners, raising awareness. Successfully arranged for the Household Support Fund for October 2024 to March 2025 to be in place for distribution.
Financial Summary | Support residents with the cost of living | 2.1b | Implement new simplified and targeted Council Tax Support scheme for 2025/26 | Resources | Revenues and Benefits | Lisa Black | Green | Ongoing - various design principles have been tested and the next meeting with the steering group is 31.3.25. The recent announcements regarding Local Government Reorganisation, along with the upcoming Spring budget may need to be considered and may influence the extent of the change. Following the meeting on 31.3.25, two options for a new banded scheme are being progressed to Labour Group which is scheduled for 6th May 2025. | With the new Government suggesting changes to Council Tax (eg possible removal of Single Person discounts), coupled with the need to review other aspects of Council Tax premiums and discounts locally and the extension of the Household Support Fund, the scheme will be developed for implementation in 26/27.
| Support residents with the cost of living | 2.1c | Deliver Round 5 of the Household Support Fund (funded by Government) before September 2024 and review Discretionary Housing Policy to meet emerging and ongoing need | Resources | Revenues and Benefits | Lisa Black | Green | HSF Round 6 - ends on 31st March 2025 with the Management Information on awards being collated and returned to DCC by mid April. The service has delivered the distribution of the full allocation and has requested from DCC the details on their approach for the next round of Household Support Fund announced in the Chancellor's autumn budget. The Chancelloer's autumn budget confirmed that Two tier LA's would receive further Household Support Funding. Derbyshire County Council are reviewing the scope of their HSF (7) and a premlimary meeting is scheduled for 17th April with DCC to obtain an understanding of distribution. It is not intended to change the design of a local scheme in the event that EBC receives funding and governance of the scheme is delegated to the Director of Finance. | Round 5 delivered. The council spent over £139,000 helping c. 140 households paying bills, helping people who are struggling with their rent and preventing people becoming homeless. EBC is now gearing up for HSF6 and is in direct liaison with DCC to ensure a timely response to any allocation for the period October 2024 to March 2025. Round 6 now in place and distribution commenced.
Risks | Support residents with the cost of living | 2.1d | Signpost and refer those in need to advice and support, including Armed Forced personnel and veterans | Resources | Revenues and Benefits | Lisa Black | Green | The business case to make direct debt referrals into CAB has been approved. This one year project is funded within the Revenues and Benefit budget and the scope of the project is being built into the existing SLA that EBC already have with CAB. This will enable upto 400 debt cases to be referred in from the Council Tax service with a view to obtaining sustainable repayment plans for households with multiple debts. This element of the SLA will be monitored directly with CAB on a quarterly basis to measure effectiveness and outcomes. | Quarterly liaison meetings with CAB are in place. Business case required to look at how EBC may fund direct debt advice so that direct referrals can be made for households experiencing financial vulnerability. Business case received from CAB to be progressed as part of a comprehensive review of debt recovery practices for Council Tax
| Improve housing access and standards | 2.2a | Reinvigorate and refresh the Homelessness & Rough Sleeping Strategy for Erewash and respond to an increase in demand for homelessness services | Environmental & Community Services | Housing Renewal | Nick Thurstan | Green | Service review report completed. Next step is to consider the recommendations and consider which should be incorporated into the next strategy. Review of homelessness from previous strategy being pulled together for scrutiny to consider at the next scrutiny meeting on 19.06.2025. | This will be developed on the back of the service-led review of Housing Options, supported by Shelter, which is nearing completion and will help identify the objectives and establish the principal actions for the strategy. The developed draft will need internal and external consultation prior to CMT and Executive consideration. Service review likely to continue to end of 24/25. Work on strategy to begin in 25/26.
| Improve housing access and standards | 2.2b | Establish an action plan for improving the quality of supported accommodation and reducing the growth in non-registered providers with partners | Environmental & Community Services | Housing Renewal | Nick Thurstan | Green | MHCLG has announced funding to continue the Supported Housing Improvement Programme for another year. Following the service restructure, the Supported Accommodation Project Officer post has been made permanent. The action plan continues to be monitored by the Homelessness and Supported Accommodation Board. As mentioned at action no.20, the consultation on licensing has been announced. | The council's participation in the nationally funded Supported Housing Improvement Programme is well underway with actions identified through this and other work within the service running concurrently as overseen at the corporate Homelessness and Supported Accommodation Board. Draft action plan in place under the vision of the Board and being updated as needed. Participation in the nationally funded Supported Housing Improvement Programme ends 31 March 2025 although an action plan is in place and being monitored by Homelessness and Supported Accommodation Board.
| Improve housing access and standards | 2.2c | Take action to improve poor housing standards in the private rented sector | Environmental & Community Services | Housing Renewal | Nick Thurstan | Green | Service restructure agreed 20 March. Three people working in proivate sector housing confirmed in post, two posts advertised and one to be advertised shortly. The Renters' Rights Bill is at the Committee stage in the House of Lords. The consultation on licensing has been announced and the service is compiling a submission, incorporating wider corporate comments, in anticipation of the 15 May deadline. | Service restructure proposed to prepare the service to deliver the large government agenda in this arena. Areas include the impact of the Renters' Rights Bill, Supported Housing (Regulatory Oversight) Act 2023 and the Warm Homes: Local Grant funding offer for energy efficiency measures. Service restructure drafted. Two posts to be evaluated to determine costs of restructure. Expected to take place in January 2025 to inform decision. The Renters Rights Bill is at the Reports stage in the House of Commons and a parliamentary statement has said that the consultation on licensing, which is a key part of implementing the Supported Housing (Regulatory Oversight) Act 2023, will be announced in the New Year. The Warm Homes: Local Grant memorandum of understanding is also expected in the New Year. Work underway to develop revised enforcement policies for member consideration including options for civil penalties.
| Improve housing access and standards | 2.2d | Develop a Housing Assistance Policy under the Regulatory Reform Order to enable Disabled Facilities Grant funding to be used more flexibly | Environmental & Community Services | Housing Renewal | Nick Thurstan | Green | An interim Disability Design Team service for 25/26 has been agreed with Derbyshire County Council, and the SLA has been signed. Further priority work underway on contracting with N-able to fill gaps in service provision. Negotiating service proposal now. Work on a discretionary Housing Assistance Policy will follow that, subject to strategy resources being available. | Early draft developed which will need to be reviewed once we have determined the financial impact of DCC's proposal to end the Disability Design Team by 31/03/25; the delivery mechanism for Disabled Facilities Grants (DFGs). There will be a cost to EBC which will come out of this budget, affecting what the policy can achieve. Negotiating an interim Disability Design Team service for 25/26 with Derbyshire County Council, following its decision to end financial support for the service. Funding available for a discretionary Housing Assistance Policy will become clearer following an agreement with DCC; if this can be reached affordably and confidence about delivery can be secured.
| Improve housing access and standards | 2.2e | Develop a longer-term strategy to increase the availability of temporary accommodation with partners | Environmental & Community Services | Housing Renewal | Nick Thurstan | Green | One property leased from Futures for use as a temporary home is in use in Ilkeston and the second one, in Sandiacre, is awaiting handover from the developer. Prim Short Stay is being used to keep bed and breakfast stays for families to an absolute minimum. | Additional resources identified to develop this plan: however, actions to increase the availability of temporary accommodation already being developed and delivered: 3 more homes leased from EMH, 12 new leased homes at a late stage of negotiation with a private-sector provider, 1 new lease from Futures planned for December, 92 EMH homes redesignated from older people to people younger than 60 to help move-on from temporary accommodation and negotiations underway to use a local hotel in the borough for some B&B. 12 new temporary homes leased from a private-sector provider now in use with an additional two new temporary homes to be leased from Futures Housing Group early in the New Year. Use of another private sector provider secured to use short-term self-contained accommodation that ensures that any stay in bed and breakfast is as short as possible for families with children or pregnant women.
| Improve quality of life | 2.3a | Actively support delivery of the Erewash Health & Wellbeing Partnership Plan to respond to the needs of targeted groups | Environmental & Community Services | Communications & Culture | Stewart Millar | Green | Erewash H&W Partnership Priorities being delivered. Ongoing delivery and development of Community Wellness Approach. Further support from H&W Partnership and involvment in Leadership of Sport England Place Expansion development phase in Kirk Hallam. | Erewash H&W Partnership Priorities reviewed and agreed with executive group. Ongoing delivery and development of Community Wellness Approach.
| Improve quality of life | 2.3b | Deliver key Shared Prosperity Fund (SPF) projects including the new 3G pitch at Rutland Sports Park and the destination play facility at West Park | Resources | Planning | Steve Birkinshaw | Completed | Both the 3G pitch at Rutlands Sports Park, and teh desintation play area at West Park completed on time. A total spend of £850,000 SPF grant funding. | West Park Play facility - 1 of 2 playgrounds complete; work underway on second. 3G pitch - work commenced, due to be completed by the end of October. Work now complete on West Park playgrounds and Rutland Sports Park 3G pitch.
| Improve quality of life | 2.3c | Work with partners to support delivery of the Erewash Community Safety Partnership Plan to respond to crime, anti-social behaviour and the fear of these | Environmental & Community Services | Communications & Culture | Stewart Millar | Green | Work ongoing to deliver against the priorities of the ECSP plan activities in 2024/25 - Neighbourhood Crime & ASB, Violence, Organised Crime and Exploitation. Sub-groups meeting and working through delivery plan actions. Some significant events saw the creation of other action groups to bring together work ongoing through a range of partners to tackle violence. | Plan approved at the Strategic Group meeting on 15.10.24 with priorities of Neighbourhood Crime and Anti-Social Behaviour, and Violence, Organised Crime and Exploitation. Delivery Plans developed to sit behind the Plan to show activity and action to deliver against the priorities.
| Improve quality of life | 2.3d | Actively support the Voluntary and Community Sector through encouraging volunteering and, where possible, financial or other support | Environmental & Community Services | Communications & Culture | Stewart Millar | Green | "Continued collaboration with the VCS, including with Erewash Voluntary Action to understand need and support local groups and organisations. SPF allocated funding saw the Community Grants pot expand through underspoend of other SPF projects, bringing a last flurry of applciations. 14 projects receiving a share of £55,743 awarded during Q1/Q2 of 2024/25. The projects anticipated that just shy of 14k individuals would be engaged through the process, with over 500 additional volunteers recruited. 2025/26 budget agreed at Full Council includes funding allocated to community grant schemes including Fast Funding, Members Grants alongside some SPF funding allocated as in previous years. " | Ongoing collaboration and conversation with the VCS, including through Erewash Voluntary Action. Fast Funding Grants to voluntary groups / organisations through UK SPF has seen 14 projects receiving a share of £17,240 awarded during Q1/Q2 of 2024/25. Work ongoing to deliver against the priorities of the ECSP plan activities in 2024/25. Sub-groups meeting and working through actions to support the delivery of actions. Year to date: Fast funding Grants totaling just shy of £30k awarded to voluntary and community groups through Fast Funding Community Grants (funded through SPF allocation). £16,280 to support Warm Spaces applications following Full Council's allocation of additional £25k to support winter activities through Warm Welcoming Spaces in Q3. Draft budget for 2025/26 includes funding allocated to replace the SPF funding stream to allow Fast Funding Grants to continue, a Members Grant Scheme and representation made for a proportion of future SPF funding to be allocated to community grants.
| Improve quality of life | 2.3e | Deliver a varied and exciting programme of events, cultural activities and museum services, alongside securing reaccreditation of Erewash Museum from Arts Council England | Environmental & Community Services | Communications & Culture | Stewart Millar | Green | Cultural Events Programme exceeded targets for 24/25. Exhibitions delivered in 2024/2025. Work progressing to achieve Arts Council England reaccreditation in 2025 or 2026 dependent on invitation from ACE. Culture Service is confident on return documentation. Museum in much stronger position than in 23/24 and work progresses to ensure long term sustainability and development with funding bids ahead of LGR. | Cultural Events Programme exceeding targets year to date. Varied programme of events during summer period. Exhibitions agreed for remainder of 2024. Work underway to achieve Arts Council England reaccreditation in 2025. Events programme exceeding targets in the year to date. Continued programme of events in Q3 and planning underway for Q4 events. Exhibitions programme continuing to be delivered in 24/25. Erewash Museum awaiting Arts Council England Accreditation return date, but work continues to progress the documentation required. Reaccreditation will now take place in 25/26.
| Improve quality of life | 2.3f | Delivery of £24.8m Long Eaton Town Deal programme, including West Park lighting scheme, Broad Street Bridge and waterside improvements | Resources | Planning | Tom Haddock | Green | Britania Mills Bridge Full Business Case Completed and Assured with Sign off by Council S.151 Officer. Full Business Case being drafted for West Park Waterfront and Broad Street Bridge Projects. Detailed Design for Long Eaton High Street. Galaxy Row - Legal drafting of Development Agreement Progressing in consultation with Council's preferred Development Partner, MyPad 2020, with agreement reached for Developer to undertake all required demolition and site clearance works. West Park Lighting Project complete. West Park Events Field Car Park Complete. | West Park Lighting Project substantially complete. Britania Mills Bridge, Broad Street Bridge and Waterfront both have obtained planning consent and are now in the detailed design stage with early contractor involvement. Galaxy Row - Procurement of Development Partner ongoing. West Park Lighting Project complete. West Park Events Field Car Park Complete. Britania Mills Bridge now progressing through Full Business Case Stage, Broad Street Bridge and Waterfront both have obtained planning consent and are now in the detailed design stage with early contractor involvement. Galaxy Row - Preferred Development Partner identified and Legal Contracts being drafted. Long Eaton High Street 2D design completed and public consultation exercise commence on 06 Jan 2025.

## Priority 3
Sustainable Environment Actions
Reporting period
Q4 2024-25
Summary All actions have commenced and are progressing to target. Quarter 1-3 updates are provided for reference. As the plan progresses, we will provide a summary of all previous updates, in addition to the latest position.
[5 empty] | Red | 0 | 0%
Home |  |  |  |  | Amber | 0 | 0%
[5 empty] | Green | 10 | 100%
Summary |  |  |  |  | Completed | 0 | 0%
Delivery Plan |  |  |  |  | Not started | 0
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Performance Indicators | Objective | Corporate Strat Ref | Action | Directorate | Service | Owner | RAG | Latest update | Previous updates
| Deliver and respond to climate change | 3.1a | Publish an Annual Climate Change Statement as well as engage and raise awareness of actions residents and partners can take in response to climate change | Environmental & Community Services | Regulatory & Housing Services | Nick Thurstan | Green | The Annual Climate Change Statement for 2023/24 was approved by the Councill Executive on 25 February 2025. The council's web site now has new climate change pages that mirror the key priorities in the Climate Change Strategy 2025-30 and include general information on how busiensses and residents can take action to reduce greenhouse gas emissions and adapt to a changing climate. Further business and community engagement will be undertaken during the coming year. | The council's first annual climate change statement for 2022-23 was approved by the Council Executive on 24 February 2024. The annual statement for 2023-24 is due to be considered by the Council Executive on 25 February 2025.
Financial Summary | Deliver and respond to climate change | 3.1b | Establish and publish a new corporate Climate Change Strategy and action plan | Environmental & Community Services | Regulatory & Housing Services | Nick Thurstan | Green | The Climate Change Strategy 2025-30 was approved by Council on 6 March 2025 and has since been published on the council's new web site. COMPLETED. | Key headline content for the strategy was agreed by the Climate Change Action Working Group on 11/9/2024. Draft strategy completed whcih is due to be considered by teh Council Executive on 25 February 2025.
| Deliver and respond to climate change | 3.1c | Pursue opportunities for investment (when available/externally secured) to support decarbonisation of the council’s operations, property and fleet assets | Environmental & Community Services | Operational Services | Dave Bramwell | Green | Fleet review underway, including consideration of alternative fuel use. Ongoing schemes for decarbonisation works at the leisure centres following successfully securing £2.8m of external grant funding. Property and Estates to liaise with the Climate Change Officer regarding further schemes and external grant opportunities. | Fleet review underway, including consideration of alternative fuel use. Ongoing schemes for decarbonisation works at the leisure centres following successfully securing £2.8m of external grant funding. Property and Estates to liaise with the Climate Change Officer regarding further schemes and external grant opportunities.
Risks | Deliver and respond to climate change | 3.1d | Facilitate the promotion and retrofitting of energy efficiency measures and low carbon technologies in eligible residential properties | Environmental & Community Services | Regulatory & Housing Services | Nick Thurstan | Green | Project Coordinator (Home Retrofit) post made permanent on 20 March and postholder confirmed in post. By the end of March 2024, all three programmes (HUG2, UKSPF and Devolution) had been delivered with 43 households benefitting from 45 measures. Two voluntary groups also benefitted from the innovative Charity Buildings programme which supported local charities through a reduction in energy costs. Erewash’s allocation for the Warm Homes: Local Grant scheme is £819,500 across a three-year programme to March 2028, with the possibility for more funding (and two additional years) following the next HM Treasury Spending Review. Analysis of carbon emissions reductions is incomplete but data from the Shared Prosperity Fund estimates 27.3 tonnes of carbon dioxide is the reduction resulting from the combined energy efficiency and renewable energy measures installed - the equivalent of flying from London to Sydney nine times. | Dedicated officer in place (fixed-term) to lead programmes with Home Upgrade Grant Phase 2 (HUG2), UK Shared Prosperity Funding (UKSPF) and Devolution funding projects all being delivered. 32 households have benefitted to date with a further 8 anticipated to benefit by year end. Solar panels and wall insulation are the most common measures. Service about to express an interest in the new national funding for energy efficiency measures, Warm Homes: Local Grant (WH:LG) from April 2025. By the end of 2024, 34 households had received energy efficiency measures and low carbon heating technology with a maximum 12 more installations planned by financial year end. An expression of interest was submitted to the Midlands Net Zero Hub (part of Nottingham City Council) for Erewash to continue to work in partnership with the consortium and be part of the application for the forthcoming Warm Homes: Local Grant programme starting in April.
| Implement new waste management | 3.2a | Implement new statutory food waste household collections and promote participation | Environmental & Community Services | Operational Services | Dave Bramwell | Green | The deadline is April 2026 for household food waste collections with confirmation awaited on national revenue funding. (Transitional funding has been allocated and awaiting updates on ongoing deliver funding). Appropriate refuse collection vehicles ordered and awaiting delivery utlising the national capital funding allocation. Work continues to develop the plans to implement the new service. The commercial waste collection service starts on 1st April 2025 and EBC are working with local schools initially. Internal processes have been implemented as of 1st April to separate and collect food waste at each of our main buildings. | The deadline is April 2026 for household food waste collections with confirmation awaited on national revenue funding. Appropriate refuse collection vehicles ordered and awaiting delivery utlising the national capital funding allocation. Work continues to develop the plans to implement the new service. Consideration is also being given to the implications for the commercial waste collection service which is subject to different deadlines.
| Implement new waste management | 3.2b | Encourage residents to produce less waste and recycle more | Environmental & Community Services | Operational Services | Dave Bramwell | Green | New recycling contract in place. Feedback from provider monitored, with regular meetings, which will assist the council to deliver targeted campaigns via social media and press releases, where required. | New recycling contract in place. Feedback from provider monitored, with regular meetings, which will assist the council to deliver targeted campaigns via social media and press releases, where required.
| Look after the borough’s green spaces | 3.2c | Implement rewilding of the borough | Environmental & Community Services | Operational Services | Dave Bramwell | Green | Previous rewilding plan implemented successfully. Following engagement and feedback, some in-year changes and amendments to schedules have been made. Discussions in place with members to finalise future modifications to the scheme and to build on the community engagement (eg links with young people/schools/friends of groups). | Previous rewilding plan implemented successfully. Following engagement and feedback, some in-year changes and amendments to schedules have been made. Discussions in place with members to finalise future modifications to the scheme and to build on the community engagement (eg links with young people/schools/friends of groups).
| Look after the borough’s green spaces | 3.3a | Establish the new Pewit Coronation Meadows local nature reserve | Environmental & Community Services | Operational Services | Dave Bramwell | Green | Work on site has commenced. So far we have installed 3 footpaths, 3 butterfly banks, litter bins and seating. On going program of works outlines actions to be completed in the coming years. Tree planting completed with mosaic habitat creation being planned for spring 2025. | Work on site has commenced. So far we have installed 3 footpaths, 3 butterfly banks, litter bins and seating. Ongoing works to achieve local nature reserve status. Tree planting commenced and due to be completed in January 2025 with mosaic habitat creation being planned for spring 2025
| Look after the borough’s green spaces | 3.3b | Maintain the high standards of West Park and Victoria Park for community use | Environmental & Community Services | Operational Services | Dave Bramwell | Green | Ongoing maintenance schedules at both sites as agreed with members, with a view to continuing the provision of high quality green spaces. | Ongoing maintenance schedules at both sites as agreed with members, with a view to continuing the provision of high quality green spaces.
| Look after the borough’s green spaces | 3.3c | Continue the provision of sports pitches and play parks across the borough | Environmental & Community Services | Operational Services | Dave Bramwell | Green | Junior football pitch added at West Park. Maintenance of all other relevant sites continues. | Junior football pitch added at West Park. Maintenance of all other relevant sites continues.

## Priority 4
A Modern Council Actions
Reporting period
Q4 2024-25
Summary All commenced actions are on target, with five already completed. Just one action not started yet, the Invest to Save policy. This is still expected to be completed within the first 2 years of the Corporate Strategy action plan. Quarter 1-3 updates are provided for reference. As the plan progresses, we will provide a summary of all previous updates, in addition to the latest position.
[5 empty] | Red | 0 | 0%
Home |  |  |  |  | Amber | 0 | 0%
[5 empty] | Green | 7 | 58.33%
Summary |  |  |  |  | Completed | 5 | 41.67%
Delivery Plan |  |  |  |  | Not started | 1
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Performance Indicators | Objective | Corporate Strat Ref | Action | Directorate | Service | Owner | RAG | Latest update | Previous updates
| Make best use of resources | 4.1a | Review of the Council Constitution to enable more efficient ways of working | Resources | Law & Governance | Danielle Hughes | Green | The Contract Procedure Rules were approved by Council In January, to add to the Financial Regulations being approved earlier in the year. We continue to review the Constitution with a view to prioritising the next updates. | The Financial Regulations have been reviewed and are due to be considered by Full Council on 31/10/2024. The Contract Procedure Rules are also being reviewed and will come to Full Council in due course. The Financial Regulations were approved by Full Council on 31/10/24. The Contract Procedure Rules will be going to General Purposes Committee for comments in January (2025), followed by Full Council in March.
Financial Summary | Make best use of resources | 4.1b | Introduce a new workforce development strategy aimed at developing a suitably skilled, motivated and engaged workforce | Resources | Human Resources | Jo Watts | Green | This was presented to and approved by the Executive in October. The council is investing £80,000 into staff training and recruiting a Learning and Development officer to support improvements in front line departments. Progress is being made on delivering key elements including new e-learning platform rolled out, new intranet in place and new staff benefits scheme introduced. | This was presented to and approved by the Executive in October. The council is investing £80,000 into staff training and recruiting a Learning and Development officer to support improvements in front line departments. Progress is being made on delivering key elements including new e-learning platform rolled out, new intranet in place and new staff benefits scheme introduced.
| Make best use of resources | 4.1c | Enhance Member and staff training and development programme | Resources | Law & Governance | Danielle Hughes/Jo Watts | Green | New Learning and Development Officer started on 31 March 2025. Corporate Learning and Development plan in development following discussions with Heads of Service. SkillGate e-learning mandatory courses released and allolcated to staff with 50% completion rate at end of Q4. Member Development Programme in development in Elections, Democratic and Civic Services. | A member survey is currently in circulation (closing date October 24). This will help inform the draft Member Development Programme. The new E-Learning platform will be live in the new year for staff and Members. Following the member survey, we have completed a first draft Member Development Programme. The new E-learning platform was launched in December 2024.
Risks | Make best use of resources | 4.1d | Develop and implement new Property Asset Management Plan including the disposal of surplus council assets | Environmental & Community Services | Property & Estates | Tom Haddock | Green | Following the Devolution White Paper published by the Government on 16 December 2024, which included the proposals for government’s intended reorganization of local government, the council has been carefully considering the potential impact. Owing to the high level of uncertainly over the future lifespan of council assets, including the unknown requirement of any new unitary authority, it has been determined not to proceed with the next stage of the Town Hall Options Appraisal at this time. | Property Asset Management Plan approved by the Council Executive on 01 October 2024, subject to call in. The council is continuing with its asset disposal plan and with improvements to current assets such as leisure centres using government grants. Property Asset Management Plan (PAMP) approved by the Council Executive on 01 October 2024. Ongoing progression of PAMP Action Plan items such as progression of Town Hall Options Appraisal to recommended shortlist of options, progression of Land Review and Car Park Review
| Make best use of resources | 4.1e | Develop a modern approach to communication with an emphasis on refreshing the approach to consultation and engagement and consultation | Environmental & Community Services | Communications & Culture | Stewart Millar | Green | New consultation and engagement platform, Let's Talk Erewash launched in January 2025, with the Budget Survey. Further awareness events developed and delivered across staff, whilst additional staff training and familiarisation continued during Q4. Briefing Session planned in very early Q1 2025/26 to Senior Management Team to further share the opportunities that the new platform can bring. The communications e-newsletters continue to build audience with the public e-newsletter achieving 7,000 subscriptions and a 76% open rate which is way above the industry average. The staff e-newsletter has been well received and a recent issue on cybercrime achieved an 80% plus open rate. The LGA carried out an independent communications health check in March and the newly designed corporate website was launched in early April. | A new monthly e-newsletter for residents was launched in September, backed by a successful marketing communications programme – subscription levels of 5k plus have been achieved over a short period and an open rate of 74% registered for the October newsletter, well above the average of 40% for other public sector organisations. A staff e-newsletter has also been developed and was launched in November. New Corporate Style Guide completed - the style guide moves away from traditional branding elements and embraces a more modern and accesible aesthetic. It aims to Enhance the council's public image by presenting a consistent and professional image across all communication channels; Improve brand recognition by establishing a clear and memorable identity for the council; Improve communication effectiveness by ensuring all communications are clear, concise, and easy to understand for our residents; Streamline design processes providing clear guidelines for staff and external partners on the use of logos, colours, typography, and imagery. New online networks launched including public e-newsletter, staff e-newsletter, and new consultation platform, Engagement HQ. Staff training continues on the new public consultation and engagement platform, Let's Talk Erewash, which is expected to be launched in January 2025– this will help improve engagement, consultation, and resident participation.
| Ensure financial stability | 4.2a | Deliver planned savings in 2024/25 and a balanced budget in 2025/26 | Resources | Accountancy | Judy Fay | Completed | Balanced budget for 2025/26 set. Monitoring of savings achieved is reported quarterly to Council Executive. | Budget development in progress. Monitoring of savings achieved is reported quarterly to Council Executive.
| Ensure financial stability | 4.2b | Develop a ten-year capital programme setting out long term investment and maintenance plans | Resources | Accountancy | Judy Fay | Green | The long term capital programme is 90% complete. With the advent of Local Government Reorganisation, the Council will defer any further work for now. | The long term capital programme is 90% complete. With the advent of Local Government Reorganisation, the Council will defer any further work for now.
| Ensure financial stability | 4.2c | Develop Invest to Save Policy to provide a framework for investment | Resources | Accountancy | Judy Fay | Not started | Due to start in 2025/26. For now, any invest to save initiatives will be considered on a case by case basis. | Due to start in 2025/26. For now, any invest to save iniatives will be considered on a case by case basis.
| Ensure financial stability | 4.2d | Develop Productivity Plan as required by Government | Resources | Accountancy | Judy Fay | Completed | Productivity Plan reported to Council Executive July 2024. We have had no feedback from Government other than a letter confirming that the "asks" made of Government will be considered. | Productivity Plan reported to Council Executive July 2024. We have had no feedback from Government other than a letter confirming that the "asks" made of Government will be considered.
| Ensure financial stability | 4.2e | Respond to Government funding consultation and lobby for additional funding for Erewash | Resources | Accountancy | Judy Fay | Completed | The Council has responded to all finance consultation this year making the case for increased funding for Erewash. | Spending Review submission completed by the Director of Resources based on the Productivity Plan produced and agreed by Members.
| Utilise technology to transform service delivery | 4.3a | Develop an ICT and digital strategy (including assessment of investment required) to enable more efficient working and protect the council from cyber risk | Resources | ICT | Andy Nix | Completed | The ICT and Digital Strategy was approved in October 2024. With the investment made the Council is in the process of delivering a number of key projects including a new website (launched in April), new intranet (launched in January), improvements in the Erewash Account (planned to go live in Quarter 3 2025/26) and a new Planning and Building Control system that will be better for customers. | ICT Strategy presented to and approved by Council Executive on 1st October 2024. The council is investing over £300,000 in various projects including a new website, improvements in the Erewash Account and a new Planning and Building Control system that will be better for customers. IT Strategy published
| Utilise technology to transform service delivery | 4.3b | Implement new waste management system | Environmental & Community Services | ICT | Andy Nix | Completed | The new system was implemented successfully. The system has been used to implement Garden Waste subscriptions and improve operational efficiency in the way missed bins are dealt with. | System implemented successfully. The system has been used to implement Garden Waste subscriptions and improve operational efficiency in the way missed bins are dealt with.
| Utilise technology to transform service delivery | 4.3c | Review customer portal and options for increasing ability to transact online to support channel shift | Resources | ICT | Andy Nix | Green | This is in progress. We have identified areas where there are options for increasing ability to do things online e.g. complaints, Freedom of Information requests, road closures. Changes to the Customer Portal will happen after the new website has been implemented. | This is in progress. We have identified areas where there are options for increasing ability to do things online e.g. complaints, Freedom of Information requests, road closures. Changes to the Customer Portal will happen after the new website has been implemented.

## Performance Indicators
Key Performance Indicator library
Reporting period
Q4 2024-25 | To support the new Corporate Strategy, and in addition to the Delivery Plan, we have introduced a new suite of Key Performance Indicators (KPIs). As with the Deliver Plan Actions, these are split by Corporate Priority: 1. Economy and Regeneration 2. Supporting Communities 3. Sustainable Environment 4. A Modern Council Performance is reported quarterly, with the exception of indicators that those that are measured at year-end. For those with an outturn, a 'Red, Amber, Green' rating, to show whether the indicator has met target. A summary table for progress against each priority is available on each priority page, with overall progress against the plan noted on the 'Summary' page of this dashboard.
Home
Summary
Delivery Plan
Performance Indicators
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Financial Summary
Risks

## KPI 1
Economy and Regeneration Indicators
Reporting period
Q4 2024-25
Summary 1 red indicator, for number of new homes delivered.
Home | [5 empty] | Red | 1 | 14.29%
[6 empty] | Amber | 0 | 0%
Summary | [5 empty] | Green | 6 | 85.71%
Delivery Plan | [5 empty] | Not started/annual | 0
Performance Indicators
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Financial Summary | Indicator Ref | sort | Indicator | Directorate | Service | Owner | Target | Frequency | Quarter 4 position | RAG | Commentary
| ER - 1 | -1 | Processing of major planning applications within timescales | Resources | Planning Development | Steve Birkinshaw | 90.3% | Quarterly | 97.7% | Green | There were 12 major applications processed in the year. 1 of them missed its target.
Risks | ER - 2 | -2 | Processing of minor planning applications within timescales | Resources | Planning Development | Steve Birkinshaw | 88.7% | Quarterly | 98% | Green | 100 minor applications were processed in 2024/25, with 2 of them missing the target date.
| ER - 3 | -3 | Processing of other planning applications within timescales | Resources | Planning Development | Steve Birkinshaw | 88.7% | Quarterly | 99% | Green | There were 406 'other'applications processed in the year, 402 of them within the appropriate timescale.
| ER - 4 | -4 | Percentage of major planning applications overturned on appeal | Resources | Planning Development | Steve Birkinshaw | 4% | Quarterly | 0% | Green | No decisions on major planning applications over turned at appeal in 2024/25
| ER - 5 | -5 | Percentage of non-major planning applications overturned on appeal | Resources | Planning Development | Steve Birkinshaw | 1% | Quarterly | 0.2% | Green | No decisions on non-major planning applications over turned at appeal in Q4. 506 applications in the whole year, with 1 overturned on appeal.
| ER - 6 | -6 | Number of new homes completed | Resources | Planning Policy | Steve Birkinshaw | 386 | Year-end | 194 | Red | Housing Delivery is currently low due to a number of factors: The existing local plan (Erewash Core Strategy, adopted 2014 ) was predicated on 2,000 homes being delivered on the Stanton Regeneration Site. To date, no homes have been delivered on the site. In recognition of the market factors affecting this site, the emerging Core Strategy Review allocates employment land on the northern section, which is being developed as New Stanton Park and proposes 1,000 homes on the southern section. Furthermore, the physical limitations of the existing urban areas along with viability issues in some areas, have suppressed delivery numbers. In order to address the shortfall in supply and increase delivery rates, the Core Strategy Review proposes a number of Green Belt housing sites adjacent to existing settlements.
| ER - 7 | -7 | Number of businesses supported by Erewash Partnership | Resources | Planning Policy | Steve Birkinshaw | 50 | Year-end | 67 | Green | Established businesses receive non-financial assistance and support from the partnership, under a Service Level Agreement with the council.

## KPI 2
Supporting Communities Indicators
Reporting period
Q4 2024-25
Summary Just 1 amber indicator, for licensed premises compliance.
Home | [5 empty] | Red | 0 | 0%
[6 empty] | Amber | 1 | 7.143%
Summary | [5 empty] | Green | 13 | 92.86%
Delivery Plan | [5 empty] | For info only | 0
Performance Indicators
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Financial Summary | Indicator Ref | sort | Indicator | Directorate | Service | Owner | Target | Frequency | Quarter 4 position | RAG | Commentary
| SC - 1 | -1 | The percentage of dangerous structures reported to the building control service that were responded to within 24 hours | Environmental & Community Services | Building Control | Nick Thurstan | 95% | Quarterly | 100% | Green | 16 dangerous structures reported in Q4; all responded to within 24 hours.
Risks | SC - 2 | -2 | Number of residents participating in council-run or partnered health and wellbeing programmes | Environmental & Community Services | Communications & Culture | Stewart Millar | 1800 | Quarterly | 2766 | Green | Service outperformed annual target due to addtional services secured through new projects in 24-25.
| SC - 3 | -3 | Number of visitors to Erewash Museum | Environmental & Community Services | Communications & Culture | Stewart Millar | 16000 | Quarterly | 16338 | Green | Q4 had consistent visitor figures and supported achieving the annual target.
| SC - 4 | -4 | Customer complaints responded to within timescales | Environmental & Community Services | Communications & Culture | Stewart Millar | 95% | Quarterly | 95% | Green | Only 3 responses were issued later than the 10 working days at stage one (2xBuilding Control, 1x combined service response). 4 Acknowledgements sent by Customer Service Team were late but the responses were issued on time for all of those
| SC - 5 | -5 | Number of organisations supported by Fast Fund Community Grants | Environmental & Community Services | Communications & Culture | Stewart Millar | For info | Quarterly | 44 | Green | Additional funding diverted from other project underspends into Fast Funding Grant pot.
| SC - 6 | -6 | Percentage of food safety inspections due during the year completed | Environmental & Community Services | Environmental Health | Nick Thurstan | 90% | Quarterly | 100% | Green | All inspections completed
| SC - 7 | -7 | Percentage of animal welfare premises inspections due during the year completed | Environmental & Community Services | Environmental Health | Nick Thurstan | 90% | Quarterly | 100% | Green | All inspections completed
| SC - 8 | -8 | Percentage of homelessness prevention cases received during the financial year closed with a successful outcome. | Environmental & Community Services | Homelessness | Nick Thurstan | 50% | Quarterly | 67% | Green | The % of successful outcomes is significantly higher than the target. This can be attributed to more active measures with providers of social housing to prioritise voids works for properties allocated to homeless households. In Q4 50% of all successful outcomes where due to an offer of social housing.
| SC - 9 | -9 | Percentage of homelessness relief cases received during the financial year closed with a successful outcome | Environmental & Community Services | Homelessness | Nick Thurstan | 30% | Quarterly | 85% | Green | The % of successful outcomes is significantly higher than the target. This can be attributed to more active measures with providers of social housing to prioritise voids works for properties allocated to homeless households. In Q4 50% of all successful outcomes where due to an offer of social housing.
| SC - 10 | -10 | Percentage of licensed premises compliant with licensing requirements within 21 days following initial intervention by the council | Environmental & Community Services | Licensing | Nick Thurstan | 100% | Quarterly | 96% | Amber | 83 premises were visited in 2024/25, 3 premises remain non-compliant and will require further action.
| SC - 11 | -11 | Percentage of licence applications under the Licensing Act determined within 5 working days (following consultation except where the application is referred to a Licensing and Public Protection Panel) | Environmental & Community Services | Licensing | Nick Thurstan | 100% | Quarterly | 100% | Green | All determined within 5 working days.
| SC - 12 | -12 | Percentage of homes made safe to live in where a serious hazard has been identified on inspection | Environmental & Community Services | Private sector housing | Nick Thurstan | 100% | Quarterly | 100% | Green | 10 Category 1 hazards removed/reduced within 10 private rented properties in the year to date within the specified timescales, following the Council's intervention.
| SC - 13 | -13 | Revs and bens - time (days) taken to process new Housing Benefit claims | Resources | Revenues & Benefits | Lisa Black | 19 | Quarterly | 16.7 | Green | The service has processed 628 claims throughout 24/25, with an average of 16.7 days across the year. This is 2.3 days better than the profiled target.
| SC - 14 | -14 | Revs and Bens Time (days) taken to process Housing Benefit change of circumstances | Resources | Revenues & Benefits | Lisa Black | 9 | Quarterly | 6.2 | Green | The service has processed 7690 Housing Benefit changes in the year in an average of 6.2 days. This is 2.8 days better than the profiled target.

## KPI 3
Sustainable Environment Indicators
Reporting period
Q4 2024-25
Summary Three amber indicators, all for Waste and Recycling. The ones for household waste are always reported one quarter in arrears as the data is not available until submitted to government, usually after the reporting period for the relevant quarter.
Home | [5 empty] | Red | 3 | 42.86%
[6 empty] | Amber | 2 | 28.57%
Summary | [5 empty] | Green | 2 | 28.57%
Delivery Plan | [5 empty] | Not started/annual | 0
Performance Indicators
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Financial Summary | Indicator Ref | sort | Indicator | Directorate | Service | Owner | Target | Frequency | Quarter 4 position | RAG | Commentary
| SE - 1 | -1 | Percentage of permits for polluting industrial processes due during the year completed | Environmental & Community Services | Environmental Protection | Nick Thurstan | 0.9 | Quarterly | 1 | Green | Completed
Risks | SE - 2 | -2 | Percentage of Environmental Protection first responses to service requests completed within 3 working days | Environmental & Community Services | Environmental Protection | Nick Thurstan | 90% | Quarterly | 99.6% | Green | Completed
| SE - 3 | -3 | Residual waste per household (kg) | Environmental & Community Services | Waste and Recycling | Dave Bramwell | No more than 364.5 | Quarterly | 393.15 | Amber | Outturn is for Quarter 3 2024-25, reported one quarter in arrears and is 8% over target. This indicator is measured cumulatively, with a profiled target throughout the year.
| SE - 4 | -4 | Household waste recycling/composting rate | Environmental & Community Services | Waste and Recycling | Dave Bramwell | 42% | Quarterly | 37.2% | Red | Outturn is for Quarter 3 2024-25, reported one quarter in arrears. This indicator is measured cumulatively.
| SE - 5 | -5 | Recycling contamination rate | Environmental & Community Services | Waste and Recycling | Dave Bramwell | No more than 10.5% | Quarterly | 16.99% | Red | Outturn is for Quarter 3 2024-25, reported one quarter in arrears as Q4 data not yet available. This indicator is measured cumulatively.
| SE - 6 | -6 | Number of missed bins per 100k collections | Environmental & Community Services | Waste and Recycling | Dave Bramwell | No more than 105 | Quarterly | 107.62 | Amber | Outturn is for Q1-Q4 2024-25 and was 2% over target. This indicator is measured cumulatively.
| SE - 7 | -7 | Reduction in the council's CO2 emissions | Environmental & Community Services | Environmental Protection | Nick Thurstan | Reduction | Year-end | 2% | Red | Gross annual greenhouse gas emissions across all the council’s main operations, including leisure, increased by 2% in 2023/24 compared to the previous year. Emissions attributed to the fleet and from leisure increased whereas the emissions from Bramcote crematorium, mains gas supply and use, business travel and purchased electricity (transmission and distribution) all reduced. The overall increase is however marginal and equivalent to an additional 38tCO2e of greenhouse gas emissions. The increase however is most likely due to energy consumption during 2022/23 being lower than normal in key operations such as leisure and fleet due to exceptional weather conditions ie drought, low rainfall and high temperatures. Energy consumption and greenhouse gas emissions observed during 2023/24 are more likley to be typical of a normal year rather than indicating an upward trend in emissions. Data collected in future years should provide more clarity on long term trends in the council's greenhouse gas emissions.

## KPI 4
A Modern Council Indicators
Reporting period
Q4 2024-25
Summary Two red indicators. Details are below but both are subject to minor variances making them red.
Home | [5 empty] | Red | 2 | 13.33%
[6 empty] | Amber | 3 | 20%
Summary | [5 empty] | Green | 10 | 66.67%
Delivery Plan | [5 empty] | Not started/annual | 0
Performance Indicators
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Financial Summary | Indicator Ref | sort | Indicator | Directorate | Service | Owner | Target | Frequency | Quarter 4 position | RAG | Commentary
| AMC - 1 | -1 | Post vacancy rate | Resources | Human Resources | Jo Watts | Not more than 12% | Quarterly | 20% | Red | In common with other councils, recruitment and retention continues to be a challenge. There is no one specific cause and the council is trying a number of different approaches to address this issue.
Risks | AMC - 2 | -2 | Number of data breaches referred to ICO | Resources | Law & Governance | Danielle Hughes | 0 | Quarterly | 1 | Red | There was one confirmed personal data breach in Quarter 4; it was low risk and not referred to the ICO. For the year, there were 10 breaches in total, with one referred to the ICO.
| AMC - 3 | -3 | Percentage of FOI and EIR requests processed within 20 working days | Resources | Law & Governance | Danielle Hughes | 95% | Quarterly | 98% | Green | There were 1,698 requests in the year (740 FOI, 958 EIR). This was up by almost 37% on the previous year. One factor in this was the increase in Land Charges EIR requests, with a rush to complete house sales prior to the increase in Stamp Duty.
| AMC -4 | -4 | Percentage of Subject Access Requests processed within 1 month | Resources | Law & Governance | Danielle Hughes | 95% | Quarterly | 90.9% | Green | 27 SARs processed in 2024-25; 2 took over 2 months due to the complexity of the cases
| AMC - 5 | -5 | Percentage of agendas published 5 working days before meetings | Resources | Law & Governance | Danielle Hughes | 95% | Quarterly | 97.1% | Green | 46 agendas were published in 2024/25. November Long Eaton Town Deal agenda was one day late due to a software issue; Legal requirement to post the meeting summons outside of all town halls was met and was included on the council's external website.
| AMC - 6 | -6 | Percentage of minutes published 10 working days following meetings | Resources | Law & Governance | Danielle Hughes | 95% | Quarterly | 91.7% | Amber | 41 sets of minutes were been published in 2024/25. 3 were published late, none of these were in quarter 4.
| AMC - 7 | -7 | Land charges requests processed within 10 working days | Resources | Law & Governance | Danielle Hughes | 95% | Quarterly | 99.9% | Green | There were 2,336 Land Charges requests processed in the year to date, with 3 missing the response target. The average response time is 11.4 working days
| AMC - 8 | -8 | Business Rates Collection rates (NNDR) - in year | Resources | Revenues & Benefits | Lisa Black | 97% | Quarterly | 80.15% | Amber | The service has collected £24,028m against a net collectable of £25,032m. This represents £253k behind the profiled target. This collection figure should be read in conjunction with the historic debt collection figure.
| AMC - 9 | -9 | Council Tax Collection rates - in year | Resources | Revenues & Benefits | Lisa Black | 95.9% | Quarterly | 81.22% | Amber | The service has collected £71.56m against a net collectable of £74.77m. This is £133k behind the profiled target. This collection figure should be read in conunction with the historic debt figure. This indicates that households are trying to maintain payments agaisnt current year and arrears.
| AMC - 10 | -10 | Building Control service to achieve 3 year rolling break even | Environmental & Community Services | Building Control | Nick Thurstan | 75% | Year-end | 89% | Green | 2024/25 was year 1 of the three year rolling cycle. The total net position of the trading account at 31 March 2025 was a deficit of £19k including partner contributions. This is a significantly improved position compared to 2023/24 in which the trading account outturned at £180k deficit. However only a nominal sum in partner contributions was received that year as an agreement was reached with partners on a model for calculating partner contributions for future years. The direction of travel in 2024/25, in which full financial contributions were received from all partners, is positive representing an 89% reduction in the trading account deficit compared to the 2023/24 outturn.
| AMC - 11 | -11 | Average phone call wait time for the Contact Centre (minutes) | Environmental & Community Services | Communications & Culture | Stewart Millar | 6 mins | Quarterly | 3.1 mins | Green | Leave managed to ensure maximum cover once GW subscription period went live
| AMC - 12 | -12 | Balanced budget for next 2 years | Resources | Accountancy | Judy Fay | Yes | Quarterly | Yes | Green | Balanced budget set for 2025/26
| AMC - 13 | -13 | Reserves projected to be of minimum for next 2 years | Resources | Accountancy | Judy Fay | Yes | Quarterly | Yes | Green | Based on the current MTFP, this is forecast to be achieved
| AMC - 14 | -14 | Statement of accounts published by May statutory deadline | Resources | Accountancy | Judy Fay | Yes | Quarterly | 96.6 | Green | 2023/24 Statement of Accounts published by 31 May deadline
| AMC - 15 | -15 | Percentage of invoices paid on time | Resources | Accountancy | Lisa Black | 95% | Quarterly | 96.47% | Green

## Financial
Reporting period | Financial Summary
Q4 2024-25 | The Council's performance against its budget is reported quarterly to the Council Executive and to Scrutiny. More information about how we are doing can be found there. We have listed below, for information, a range of financial indicators – some of which are outside the control of the Council
Home
Summary
|  | Indicator ref | Indicator | Directorate | Service | Owner | Target | Quarter 4 position | RAG | Comments
Delivery Programme |  | FS1 | Total core spending power per dwelling | Resources | Accountancy | Judy Fay | For info | 238 | For info | The core spending power is extracted from the local government financial settlement. CSP for 2023-24 was £225, increasing to £238.
|  | FS2 | Total debt as percentage of core spending power | Resources | Accountancy | Judy Fay | 0 | 0% | Green | The council has zero long term borrowing
Performance Indicators |  | FS3 | Non-ringfenced reserves as percentage of net revenue expenditure | Resources | Accountancy | Judy Fay | For info | 0 | Annual | Year end not yet finalised
|  | FS4 | Council tax revenue per dwelling | Resources | Revenues & Benefits | Lisa Black | For info | 141.31 | For info | Figure based on the local government finance settlement
Financial Summary |  | FS5 | Level of band D council tax rates | Resources | Revenues & Benefits | Lisa Black | For info | 213.83 | For info | This is the council tax for Erewash only, excludes police, fire etc.
|  | FS6 | Debt servicing as percentage of core spending power | Resources | Accountancy | Judy Fay | For info | 0% | Green | Council has zero long term borrowing
Risks |  | FS7 | Balanced budget for current year | Resources | Accountancy | Judy Fay | For info | Yes | For info | Balanced budget set for 2024/25
|  | FS8 | Gross external debt | Resources | Accountancy | Judy Fay | Yes | 0% | Green | Council has zero long term borrowing
|  | FS9 | Auditor approved accounts | Resources | Accountancy | Judy Fay | For info | No | For info | 2021/22 accounts approved, 2022/23 disclaimed, 23/24 disclaimed. All audits now back up to date

## Risks
Risks
Reporting period
There have been two significant changes in the Strategic Risk Register this quarter. Risk 5 (ICT infrastructure) has been removed, as it is no longer considered a strategic risk. And there is a new risk (Risk 10 - Government Devolution). Otherwise, the only change has been Risk 2 (ICT Financial Stability) moving from red to amber (see below). For more information, please see the February 2024 Audit Committee Strategic Risk Register, once published, at the link below.
Q4 2024-25
Home
Summary
Delivery Plan
Performance Indicators
Financial Summary |  |  |  | https://moderngov.erewash.gov.uk/ieListDocuments.aspx?CId=285&MId=2386
Risks |  | Risk | Description | Date added | Inherent risk score | Residual risk score | Latest movement | Latest update
|  | Risk ID 1 – Key priorities delivery | There is a risk we cannot deliver key/new priorities due to a lack of resources caused by retention/recruitment issues, budget or too big a corporate workload (including additional requirements from Government). | 2023-05-01 | 20 | 12 | çè | Controls updated to reflect new 4-year people strategy now approved, investment in training budget agreed and new employee benefit scheme launched in Dec 24. New action added in light of local government reorganisation proposals.
|  | Risk ID 2 – Financial stability | There is a risk that the Council is not financially stable in the medium term (as evidenced by the gap in MTFF) due to uncertain future government funding. | 2019-06-01 | 25 | 20 | é | Reduction in risk score from 20 (red) to 12 (amber) due to balanced budget for 25/26 and sufficient reserves for next few years.
|  | Risk ID 3 – Housing land supply | Failure to demonstrate adequate housing land supply resulting in various impacts - a shortfall each year in property available for sale, house price inflation, local residents leaving the Borough or new people not moving in and loss of council tax base of £225,000 per year. | 2016-07-01 | 15 | 12 | çè | No change to risk profile – updates to controls and comment section to reflect Government confirmed higher housing targets.
|  | Risk ID 4 – Long Eaton Town Board | The Town Board not able to deliver on one or more of its key projects resulting in failure to meet objectives, financial loss, reputational damage and frustration for residents. Risk includes construction cost inflation, council capacity to develop multiple projects, contractor administration risk, delays in design agreements, funding restricted to committed costs and completion deadline. | 2022-03-01 | 16 | 9 | çè | No changes made New actions added to reflect monitoring of cost inflation.
|  | Risk ID 5 – ICT infrastructure | Lack of appropriate ICT/digital infrastructure undermines Council’s ability to deliver on its priorities and/or creates inefficiencies. | 2023-03-01 | - | - |  | Closed. It is considered that with the existing structure, controls, new ICT Strategy now in place and intranet and website developments underway this is no longer a strategic risk and is therefore closed as of January 2025.
|  | Risk ID 6 – Business Continuity | Failure to deliver key services should a significant business interruption occur. | 2023-05-01 | 16 | 9 | çè | NNo change to risk profile. Completed action documented following Cyber Security exercise in November 24 and prioritisation of service function recovery.
|  | Risk ID 7 – GDPR compliance | Information Governance / GDPR Risk: There is a risk that the Council suffers a data protection breach arising from poor processes and controls, accidental or intentional actions including cyber attack, leading to potential harm to individuals, employees and members, legal action, financial penalties from ICO and reputational damage. | 2023-12-01 | 20 | 6 | çè | No change to risk profile. Controls embedded via policies, procedures and training.
|  | Risk ID 8 – Temporary Accommodation | There is a risk of significant overspend on supported housing and temporary accommodation, in order for the Council to deliver its duty on homelessness under the Housing Act 1996 and manage its duty around accommodation of families with children/pregnant women. | 2023-12-01 | 25 | 20 | çè | No change to risk profile. Actions and comments updated to reflect agreement and activities to purchase new properties to help with temporary accommodation.
|  | Risk ID 9 – Cyber Attack | Cyber attack against the Council preventing delivery of critical services and/or breach or corruption of data. | 2024-09-01 | 12 | 12 | çè | No change to risk profile. Actions, controls and comments updated.
|  | Risk ID 10 - Government Devlotion | The impact of the Government’s Devolution White Paper creates some medium-term uncertainty which could have impacts on workforce (recruitment, retention and capacity), financial planning, and service delivery resulting in difficulties in delivering business as usual. | 2025-01-01 | - | 20 | New | New risk added. Residual Risk score 20 (impact 4 x likelihood 5)

## Lookup (hidden)
Q2 2024-25 | 2024-09-30 | Q2 2024-25
Q3 2024-25 | 2024-12-31 | Q3 2024-25
Q4 2024-25 | 2025-03-31 | Q4 2024-25
Q1 2025-26 | 2025-06-30 | Q1 2025-26
Q2 2025-26 | 2025-09-30 | Q2 2025-26
Q3 2025-26 | 2025-12-31 | Q3 2025-26
Q4 2025-26 | 2026-03-31 | Q4 2025-26
Q1 2026-27 | 2026-06-30 | Q1 2026-27
Q2 2026-27 | 2026-09-30 | Q2 2026-27
Q3 2026-27 | 2026-12-31 | Q3 2026-27
Q4 2026-27 | 2027-03-31 | Q4 2026-27
Q1 2027-28 | 2027-06-30 | Q1 2027-28
Q2 2027-28 | 2027-09-30 | Q2 2027-28
Q3 2027-28 | 2027-12-31 | Q3 2027-28
Q4 2027-28 | 2028-03-31 | Q4 2027-28
Q1 2028-29 | 2028-06-30 | Q1 2028-29
Q2 2028-29 | 2028-09-30 | Q2 2028-29
Q3 2028-29 | 2028-12-31 | Q3 2028-29
Q4 2028-29 | 2029-03-31 | Q4 2028-29
Q1 2029-30 | 2029-06-30 | Q1 2029-30
Q2 2029-30 | 2029-09-30 | Q2 2029-30
Q3 2029-30 | 2029-12-31 | Q3 2029-30
Q4 2029-30 | 2030-03-31 | Q4 2029-30
Q1 2030-31 | 2030-06-30 | Q1 2030-31
Q2 2030-31 | 2030-09-30 | Q2 2030-31
Q3 2030-31 | 2030-12-31 | Q3 2030-31
Q4 2030-31 | 2031-03-31 | Q4 2030-31
Q1 2031-32 | 2031-06-30 | Q1 2031-32
Q2 2031-32 | 2031-09-30 | Q2 2031-32
Q3 2031-32 | 2031-12-31 | Q3 2031-32
Q4 2031-32 | 2032-03-31 | Q4 2031-32
Q1 2032-33 | 2032-06-30 | Q1 2032-33
Q2 2032-33 | 2032-09-30 | Q2 2032-33
Q3 2032-33 | 2032-12-31 | Q3 2032-33
Q4 2032-33 | 2033-03-31 | Q4 2032-33
Q1 2033-34 | 2033-06-30 | Q1 2033-34
Q2 2033-34 | 2033-09-30 | Q2 2033-34
Q3 2033-34 | 2033-12-31 | Q3 2033-34
Q4 2033-34 | 2034-03-31 | Q4 2033-34