## About
Erewash Borough Council Performance Dashboard
Click on the links below to navigate the dashboard
Home | About this dashboard
Summary
Delivery Plan
Welcome to Erewash Borough Council's Performance Dashboard. The dashboard reports on four main areas: 1. 'Delivery Plan'. These are high level actions/projects for strategic and operational priorities across our services for the 2024-26 financial years. They also drive and measure progress against the Corporate Strategy. There are sub-tabs for each priority against the Corporate Strategy. 2. 'Performance Indicators'. A suite of key performance indicators that measure performance across the Council's services and underpin the Corporate Strategy. Again, these are split by Corporate Strategy priority. 3. 'Financial Summary'. A summary of the latest financial position 4. 'Risks'. A summary of the latest position against the risks on the Strategic Risk Register. Navigate through the dashboard using the links on the left hand side.
Performance Indicators
Financial Summary
Risks
Click the image below to see the 2024-28 Corporate Strategy

## Summary
a
Summary
Reporting period
Welcome to the third release of the new performance framework. Below is an overall summary for Corporate Strategy Actions and Key Performance Indicators. Updates and outturns for each by corporate priority are available on the relevant pages in this dashboard.
Q4 2024-25
Home
| Summary | Corporate Strategy Actions
94% of Delivery Plan actions were on target or completed at the end of Quarter 1. For more information on the amber actions and the ones yet to start, see the individual Delivery Plan priorities.
Delivery Plan
| Performance Indicators |  | Red | 0 | 0%
|  |  | Amber | 3 | 6.383%
| Financial Summary |  | Green | 36 | 76.6%
|  |  | Completed | 8 | 17.02%
Risks
|  |  | Not started | 2
Key Performance Indicators
76% of all KPIs were on target at the end of Quarter 1, with a further 11% within their tolerance level. There were 5 red indicators; for further information on these and all indicators, see the individual priority tabs. We await the update for one indicator.
|  |  | Red | 5 | 13.51%
|  |  | Amber | 4 | 10.81%
|  |  | Green | 28 | 75.68%
|  |  | Not started/annual | 2

## Delivery programme
Corporate Strategy Delivery Plan
Reporting period
Q1 2024-25 | We have developed a 4-year 'Delivery Plan' to both drive, and measure progress against our new Corporate Strategy. The actions within the plan have been split into Years 1 & 2 (2024/25 and 2025/26), and Years 3 & 4 (2026/27 and 2027/28). The plan is divided into the four priorities, and then by the objectives for each of those priorities: 1. Economy and Regeneration Promote regeneration Progress economic growth opportunities Improve housing supply 2. Supporting Communities Support residents with the cost of living Improve housing access and standards Improve quality of life 3. Sustainable Environment Deliver and respond to climate change Implement new waste management Look after the borough’s green spaces 4. A Modern Council Make best use of resources Ensure financial stability Utilise technology to transform service delivery Performance is reported quarterly, with a 'Red, Amber, Green' rating, to show whether the action is expected to be completed by its target date. A summary table for progress against each priority is available on each priority page, with overall progress against the plan noted on the 'Summary' page of this dashboard.
Home
Summary
Delivery Plan
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Performance Indicators
Financial Summary
Risks

## Priority 1
Economy and Regeneration Actions
Reporting period
Q1 2024-25
Summary All actions have commenced and are progressing to target or completed, with the exception of 1.1a and c. Previous updates are provided for reference. As the plan progresses, we will provide a summary of all previous updates, in addition to the latest position.
[5 empty] | Red | 0 | 0%
Home |  |  |  |  | Amber | 2 | 18.18%
[5 empty] | Green | 8 | 72.73%
Summary |  |  |  |  | Completed | 1 | 9.091%
Delivery Plan |  |  |  |  | Not started | 0
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Performance Indicators | Objective | Corporate Strat Ref | Action | Directorate | Service | Owner | RAG | Latest update | Previous updates
| Promote regeneration | 1.1a | Regeneration of Long Eaton High Street and creation of new managed workspace units at the Stable Block | Resources | Planning | Steve Birkinshaw | Amber | High Street - Awaiting target cost of approved design. Stable Block - Still in construction phase. | Long Eaton High St - Design ongoing through Derbyshire County Council partners. Construction expected to be completed Summer/Autumn 2026. Stable Block - Project delayed owing to defective works identified on site undertaken by previous contractor, additional costs implications still to be determined. Long Eaton High Street - significant milestone reached with General Arrangement being signed off by the Highway Authority. Stable Block - project now progressing to revised timetable. Long Eaton High Street - Public consultation confirmed support for emerging scheme design, giving confidence to develop design further towards forumulation of Target Cost. Stable Block - project at advanced stage of construction.
Financial Summary | Promote regeneration | 1.1b | Explore options for bringing empty commercial properties back into use in town centres | Resources | Planning | Steve Birkinshaw | Green | Expanded shop signage and new shop front improvement grants developed, funded by Shared Propserity Fund. | Enforcement action underway to issue Section 215 (untidy property) improvement notices. Dual purpose of improving public realm and prompting owners to bring them back into active economic use. S215 process put on hold pending launch of new property improvement grant in 2025/26.
| Promote regeneration | 1.1c | Assessment of car park need and development of a Car Park Strategy | Environmental & Community Services | Operational Services | Steve Birkinshaw | Amber | Review of Ilkeston Car Park Strategy initiated to align outcomes more closely to Council objectives. | Assessment and draft Car Park Strategy completed. Next step is progress towards internal approval. Council Executive progressing aspects of Ilkeston Car Park Strategy. Long Eaton Car Park Strategy on hold pending completion of Long Eaton High Street Town Deal project.
Risks | Progress economic growth opportunities | 1.2a | Review progress made in implementing Economic Development Strategy | Resources | Planning | Steve Birkinshaw | Green | Strategic Priority 1: Town Centres - 2 empty properties brought back into use with assistance of SPF funded Shop Signage Grant, Shop Front Improvement Grant launched with 3 positive responses to targeted approach. Strategic Priority 2: Rural Recreation - Visit Erewash marketing website continues running – link through main Erewash Borough Council home page. Strategic Priority 3: Development and Business Growth - SPF R&D grant scheme launched with 1 application so far – approvals panel due in July Q2. 31 businesses have received non-financial support, and 3 enterprises have adopted new to firm technologies/processes through support from Derbyshire Business Accelerator. Erewash Partnership continue to support local start-ups – report due in Q2. | Strategic Priorty 1: Town Centres - 16 empty properties brought back into use with assistance of SPF funded signage grant, Long Eaton High Street design progressed with Town Deal funding. Strategic Priorty 2: Rural Recreation - SPF funded Rural Erewash marketing campaign reaches 150,000 people and increases visitor numbers by 21%. Strategic Priort 3: Development and Business Growth - SPF grants support 19 retail and 11 manufacturing businesses directly, and through contract with Erewash Partnership provides advice to 436 businesses including 109 new busines start-ups creating 146 jobs.
| Progress economic growth opportunities | 1.2b | Continue to support the development of warehousing and industrial premises at the 200 acre New Stanton Park | Resources | Planning | Steve Birkinshaw | Green | Plot 1 now fully permitted and under development for 5 industrial units. Discussions on development of Plot 3 highly advanced. | Planning approval granted for 5 warehouse units on Plot 1 at New Stanton Park. Discussions underway with developers on potential further applications . Planning approval granted for electric vehicle charging facility with drive through food and drink offer, which is expected to improve the appeal of New Stanton to potential industrial occupiers.
| Progress economic growth opportunities | 1.2c | Engage and survey local businesses to identify business needs and unlock barriers to growth through the EMCCA | Resources | Planning | Steve Birkinshaw | Completed | See previous updates. | Erewash Partnership undertaking a project which includes a survey of local business Erewash Partnership survey confirms local demand for new industrial premises, including starter units. EMCCA effectively lobbied to secure local spend of SPF monies over 2025-26. New Stanton park development, provided early through the Core Strategy Review process, under development to provide for the identified need for new industrial premises.
| Progress economic growth opportunities | 1.2d | Promote entrepreneurial opportunities through SPF including research and development grants, retail signage and business grants | Resources | Planning | Steve Birkinshaw | Green | Proposals to use Shared Prosperity Fund to continue research & development and retail signage grants, and to introduce new shop front improvement grant, approved by EMCCA. | At the close of this year's SPF funding period, 19 new retail buisnesses had been supported bringing 16 vacant shop units into use, and 11 businesses provided research and development support inlcuding 6 who were new to research and development. In total these businesses received £137,527 of direct grant funding.
| Improve housing supply | 1.3a | Adopt Core Strategy subject to the results of the public examination and enable new housing development through the planning system | Resources | Planning | Steve Birkinshaw | Green | Core Strategy Review Amendment agreed at Extraordinary Council, subjected to public consultation, and submitted to Planning Inspector for examination. | The Planning Inspector issued a post hearing letter on 4 September 2024 with a set of requirements. The council has responded to confirm how it will meet these requirements over a six month period. The inspector will then consider whether the plan is ready for adoption.
| Improve housing supply | 1.3b | Develop a new Housing Strategy/approach and action plan to meet local housing need | Environmental & Community Services | Regulatory & Housing Services | Nick Thurstan | Green | The Housing Service has developed a draft which will be considered by senior officers following the imminent draft sign-off process at service level. | Objectives drafted and action plan being developed in draft form for consideration at Homelessness and Supported Accommodation Board. Once agreed, there will be a period of internal and external consultation. Strategy objectives under consideration by Portfolio Holder and draft document development underway for consideration by senior officers and members.
| Improve housing supply | 1.3c | Consider options for bringing empty residential properties back into use engaging with partners | Environmental & Community Services | Regulatory & Housing Services | Nick Thurstan | Green | The Housing Service proposed an approach at the rescheduled Homelessness and Supported Accommodation Project Board on 16 July. Following discussion with the relevant portfolio holder a report will lay out the principal advantages and potential costs for lead members. | A letter targeting owners of long-term empty homes has been drafted to gauge the level of involvement needed to tackle the 'low hanging fruit'. However, resources will need to be identified corporately to engage with landlords to make any significant impact on the many empty homes; this will be included in the draft housing strategy for consideration. Letter to owners of long-term empty homes approved and to be posted early January. Replies to letter to landlords of empty homes being received and analysed. Quick solutions to the issues raised being identified and implemented. Findings to be discussed at the corporate Homelessness and Supported Accommodation Board on 3 June to consider options for the more complex issues.
| Improve housing supply | 1.3d | With partners encourage and promote increasing the supply of affordable housing | Resources | Planning | Steve Birkinshaw | Green | Core Strategy Review Amendment agreed at Extraordinary Council, promoted an additional 8 Green Belt sites for housing, expected to deliver 328 affordable homes over the next five years. | Change in emphasis of Town Deal Galaxy Row Project will deliver affordable homes. Application underway to deliver affordable homes at the former Ilkeston Argos, funded by the EMCCA Brownfield housing fund. Currently preparing business case following success at Expression of Interest stage. Planning permission granted for 259 homes north of Spondon, including 26 Fisrt Homes (starter homes to buy) on site and a financial contribution of £5.5 million for affordable housing delivery elsewhere in the Borough.

## Priority 2
Supporting Communities Actions
Reporting period
Q1 2024-25
Summary All actions are on target or completed, with the execption of the Long Eaton Town Deal programme. Previous updates are provided for reference. As the plan progresses, we will provide a summary of all previous updates, in addition to the latest position.
[5 empty] | Red | 0 | 0%
Home |  |  |  |  | Amber | 1 | 6.667%
[5 empty] | Green | 12 | 80%
Summary |  |  |  |  | Completed | 2 | 13.33%
Delivery Plan |  |  |  |  | Not started | 0
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Performance Indicators | Objective | Corporate Strat Ref | Action | Directorate | Service | Owner | RAG | Latest update | Previous updates
| Support residents with the cost of living | 2.1a | Be an active member of the Financial Inclusion Network, deliver the cost of living action plan with partners and promote access to available support and services | Resources | Revenues and Benefits | Lisa Black | Green | The Head of service remains an active member of the regional Financial Inclusion Group. There haven't been any meetings in the first quarter and therefore no actions to progress. Leaflet made available digitally and this will be made available on website. | Head of Revenues & Benefits is an active member of the regional financial inclusion group. We have also developed links with Citizens Advice Bureaux (CAB) to develop best practice in relation to debt collection and supporting households in cyclical debt. Led the development of the response to Household Support Fund 5 and established working relationships with Derbyshire County Council leads on HSF. Update the same as Q1. Regular and routine attendance at Derbyshire wide Financial Inclusion Group. Quarterly meetings with CAB and recent business case provided to look to develop a direct relationship for debt referral in to CAB. To be progressed in line with a review of Council Tax debt recovery procedures. Worked in partnership with CAB to promote take up of Pension Credit, with a direct mailing to over 1200 pensioners, raising awareness. Successfully arranged for the Household Support Fund for October 2024 to March 2025 to be in place for distribution.
Financial Summary | Support residents with the cost of living | 2.1b | Implement new simplified and targeted Council Tax Support scheme for 2025/26 | Resources | Revenues and Benefits | Lisa Black | Completed | The current Council Tax Support Scheme has been reviewed and the decision reached that the current default scheme will remain in place. The introducton of LGR means that all CTRS schemes for the region will need to be aligned in the new organisation. | With the new Government suggesting changes to Council Tax (eg possible removal of Single Person discounts), coupled with the need to review other aspects of Council Tax premiums and discounts locally and the extension of the Household Support Fund, the scheme will be developed for implementation in 26/27.
| Support residents with the cost of living | 2.1c | Deliver Round 5 of the Household Support Fund (funded by Government) before September 2024 and review Discretionary Housing Policy to meet emerging and ongoing need | Resources | Revenues and Benefits | Lisa Black | Green | Delivery of Household support fund 7 has commenced and will run through to March 2026. The Government has announced its intent to merge Discretionary Housing Payments and Household Support Fund into a new Crisis and Resilience Fund (CRF), with expected implementation date of 1st April 2026, therefore a review of the DHP at this stage is no longer required. It is unclear as yet how the new CRF will be delivered and by whom, given that HSF is currently the responsibility of DCC (with elements devolved to the districts) and DHP sits with Revenues and Benefit services. It is fully expected that government guidance will be available in early 2026. | Round 5 delivered. The council spent over £139,000 helping c. 140 households paying bills, helping people who are struggling with their rent and preventing people becoming homeless. EBC is now gearing up for HSF6 and is in direct liaison with DCC to ensure a timely response to any allocation for the period October 2024 to March 2025. Round 6 now in place and distribution commenced. HSF Round 6 - ends on 31st March 2025 with the Management Information on awards being collated and returned to DCC by mid April. The service has delivered the distribution of the full allocation and has requested from DCC the details on their approach for the next round of Household Support Fund announced in the Chancellor's autumn budget. The Chancelloer's autumn budget confirmed that Two tier LA's would receive further Household Support Funding. Derbyshire County Council are reviewing the scope of their HSF (7) and a premlimary meeting is scheduled for 17th April with DCC to obtain an understanding of distribution. It is not intended to change the design of a local scheme in the event that EBC receives funding and governance of the scheme is delegated to the Director of Finance.
Risks | Support residents with the cost of living | 2.1d | Signpost and refer those in need to advice and support, including Armed Forced personnel and veterans | Resources | Revenues and Benefits | Lisa Black | Green | The direct referral pilot for households in financial crisis commences on 14th July 2025. The service continues to promote advice services at each stage of recovery for all residents. | The business case to make direct debt referrals into CAB has been approved. This one year project is funded within the Revenues and Benefit budget and the scope of the project is being built into the existing SLA that EBC already have with CAB. This will enable upto 400 debt cases to be referred in from the Council Tax service with a view to obtaining sustainable repayment plans for households with multiple debts. This element of the SLA will be monitored directly with CAB on a quarterly basis to measure effectiveness and outcomes.
| Improve housing access and standards | 2.2a | Reinvigorate and refresh the Homelessness & Rough Sleeping Strategy for Erewash and respond to an increase in demand for homelessness services | Environmental & Community Services | Housing Renewal | Nick Thurstan | Green | A review of actions from the last homelessness strategy was presented to Scrutiny Committee on 19.06.25. A full review of homelessness over the last five years is in progress and will be completed by autumn. The findings of the review will inform the next homelessness strategy. | Service review report completed. Next step is to consider the recommendations and consider which should be incorporated into the next strategy. Review of homelessness from previous strategy being pulled together for scrutiny to consider at the next scrutiny meeting on 19.06.2025.
| Improve housing access and standards | 2.2b | Establish an action plan for improving the quality of supported accommodation and reducing the growth in non-registered providers with partners | Environmental & Community Services | Housing Renewal | Nick Thurstan | Green | The action plan continues to be monitored by the Homelessness and Supported Accommodation Board. Growth in the supported accommodation sector has remained stable over the last 12 months. The council provided an in-depth response to national consultation on supported housing regulation, which closed on 15 May. | The council's participation in the nationally funded Supported Housing Improvement Programme is well underway with actions identified through this and other work within the service running concurrently as overseen at the corporate Homelessness and Supported Accommodation Board. Draft action plan in place under the vision of the Board and being updated as needed. Participation in the nationally funded Supported Housing Improvement Programme ends 31 March 2025 although an action plan is in place and being monitored by Homelessness and Supported Accommodation Board. MHCLG has announced funding to continue the Supported Housing Improvement Programme for another year. Following the service restructure, the Supported Accommodation Project Officer post has been made permanent. The action plan continues to be monitored by the Homelessness and Supported Accommodation Board. As mentioned at action no.20, the consultation on licensing has been announced.
| Improve housing access and standards | 2.2c | Take action to improve poor housing standards in the private rented sector | Environmental & Community Services | Housing Renewal | Nick Thurstan | Green | The Housing Service restructure is being implemented with two postholders now in permanent posts and one advert closing shortly. A consultation response on supported housing regulation was submitted on 15 May. The Renters' Rights Bill is at the Consideration of Lords Amendments stage in the House of Commons. The stage after Royal Assent, once it comes, will be to prepare for implementation of the new Act including consulting landlords on the council's draft policy on civil penalties. | Service restructure agreed 20 March. Three people working in proivate sector housing confirmed in post, two posts advertised and one to be advertised shortly. The Renters' Rights Bill is at the Committee stage in the House of Lords. The consultation on licensing has been announced and the service is compiling a submission, incorporating wider corporate comments, in anticipation of the 15 May deadline.
| Improve housing access and standards | 2.2d | Develop a Housing Assistance Policy under the Regulatory Reform Order to enable Disabled Facilities Grant funding to be used more flexibly | Environmental & Community Services | Housing Renewal | Nick Thurstan | Green | Work to develop an interim Disabled Facilities Grant service for 25/26 is progressing to be followed by the council, in partnership with many of Derbyshire's councils, initiating an options appraisal for a service from 1 April 2026. It is intended that work on a discretionary Housing Assistance Policy will start during the latter project as strategy resources become available. | Early draft developed which will need to be reviewed once we have determined the financial impact of DCC's proposal to end the Disability Design Team by 31/03/25; the delivery mechanism for Disabled Facilities Grants (DFGs). There will be a cost to EBC which will come out of this budget, affecting what the policy can achieve. An interim Disability Design Team service for 25/26 has been agreed with Derbyshire County Council, and the SLA has been signed. Further priority work underway on contracting with N-able to fill gaps in service provision. Negotiating service proposal now. Work on a discretionary Housing Assistance Policy will follow that, subject to strategy resources being available.
| Improve housing access and standards | 2.2e | Develop a longer-term strategy to increase the availability of temporary accommodation with partners | Environmental & Community Services | Housing Renewal | Nick Thurstan | Green | The Housing Service is developing a new temporary accommodation framework for bed and breakfast and nightly paid accommodation and will seek to procure providers in the autumn. It has also advertised a tender to the market for an appraisal of options to build or buy its own temporary accommodation. In March 2024, the service secured a grant of £323,199 from round 3 of the Local Authority Housing Fund to buy two homes for temporary accommodation. The service is working with EMH homes to deliver the project, and the homes are on schedule to be delivered in March 2026. A new temporary three-bedroomed home is being leased from Futures Housing Group and is expected to be ready to let to homeless families by the end of August. | Additional resources identified to develop this plan: however, actions to increase the availability of temporary accommodation already being developed and delivered: 3 more homes leased from EMH, 12 new leased homes at a late stage of negotiation with a private-sector provider, 1 new lease from Futures planned for December, 92 EMH homes redesignated from older people to people younger than 60 to help move-on from temporary accommodation and negotiations underway to use a local hotel in the borough for some B&B. 12 new temporary homes leased from a private-sector provider now in use with an additional two new temporary homes to be leased from Futures Housing Group early in the New Year. Use of another private sector provider secured to use short-term self-contained accommodation that ensures that any stay in bed and breakfast is as short as possible for families with children or pregnant women. One property leased from Futures for use as a temporary home is in use in Ilkeston and the second one, in Sandiacre, is awaiting handover from the developer. Prim Short Stay is being used to keep bed and breakfast stays for families to an absolute minimum.
| Improve quality of life | 2.3a | Actively support delivery of the Erewash Health & Wellbeing Partnership Plan to respond to the needs of targeted groups | Environmental & Community Services | Communications & Culture | Stewart Millar | Green | Erewash H&W Partnership priorities and new structure being developed into Strategic Plan 2025-2027. Further success in securing funding commitment for Community Wellness Approach until 2027. | Erewash H&W Partnership Priorities reviewed and agreed with executive group. Ongoing delivery and development of Community Wellness Approach.
| Improve quality of life | 2.3b | Deliver key Shared Prosperity Fund (SPF) projects including the new 3G pitch at Rutland Sports Park and the destination play facility at West Park | Resources | Planning | Steve Birkinshaw | Completed | Both the 3G pitch at Rutland Sports Park, and the desintation play area at West Park completed on time. A total spend of £850,000 SPF grant funding. | West Park Play facility - 1 of 2 playgrounds complete; work underway on second. 3G pitch - work commenced, due to be completed by the end of October. Work now complete on West Park playgrounds and Rutland Sports Park 3G pitch.
| Improve quality of life | 2.3c | Work with partners to support delivery of the Erewash Community Safety Partnership Plan to respond to crime, anti-social behaviour and the fear of these | Environmental & Community Services | Communications & Culture | Stewart Millar | Green | Work is ongoing to deliver against the priorities of the ECSP partnership plan in 2025/2026 - Neighbourhood Crime & ASB, Violence, organised crime & Exploitation. Sub group meetings are in place to work through delivery plan actions. Focus is given to any hotspot locations where required. | Plan approved at the Strategic Group meeting on 15.10.24 with priorities of Neighbourhood Crime and Anti-Social Behaviour, and Violence, Organised Crime and Exploitation. Delivery Plans developed to sit behind the Plan to show activity and action to deliver against the priorities. Work ongoing to deliver against the priorities of the ECSP plan activities in 2024/25 - Neighbourhood Crime & ASB, Violence, Organised Crime and Exploitation. Sub-groups meeting and working through delivery plan actions. Some significant events saw the creation of other action groups to bring together work ongoing through a range of partners to tackle violence.
| Improve quality of life | 2.3d | Actively support the Voluntary and Community Sector through encouraging volunteering and, where possible, financial or other support | Environmental & Community Services | Communications & Culture | Stewart Millar | Green | Continued collaboration with the VCS, including with Erewash Voluntary Action to understand need and support local groups and organisations. An overall amount of £65,000, including £20,000 SPF funding secured by the council, has been made available for two community grant schemes which were launched in Q2. • Member Grants – £25,000 funding made available for the year for grant awards between £2,000 and £3,500. • Fast Funding Grants – £40,000 made available for the year (including £20,000 SPF funding secured) for grant awards between £500 and £1,500. | Ongoing collaboration and conversation with the VCS, including through Erewash Voluntary Action. Fast Funding Grants to voluntary groups / organisations through UK SPF has seen 14 projects receiving a share of £17,240 awarded during Q1/Q2 of 2024/25. Work ongoing to deliver against the priorities of the ECSP plan activities in 2024/25. Sub-groups meeting and working through actions to support the delivery of actions. Year to date: Fast funding Grants totaling just shy of £30k awarded to voluntary and community groups through Fast Funding Community Grants (funded through SPF allocation). £16,280 to support Warm Spaces applications following Full Council's allocation of additional £25k to support winter activities through Warm Welcoming Spaces in Q3. Draft budget for 2025/26 includes funding allocated to replace the SPF funding stream to allow Fast Funding Grants to continue, a Members Grant Scheme and representation made for a proportion of future SPF funding to be allocated to community grants. 2025/26 budget agreed at Full Council includes funding allocated to community grant schemes including Fast Funding, Members Grants alongside some SPF funding allocated as in previous years.
| Improve quality of life | 2.3e | Deliver a varied and exciting programme of events, cultural activities and museum services, alongside securing reaccreditation of Erewash Museum from Arts Council England | Environmental & Community Services | Communications & Culture | Stewart Millar | Green | Cultural events programmed extended into 25/26 and further SPF secured including refurbishment of museum visitor areas. Work is ongoing to refine documentation ahead of ACE Accreditation, now not expected until Q4. | Cultural Events Programme exceeded targets for 24/25. Exhibitions delivered in 2024/2025. Work progressing to achieve Arts Council England reaccreditation in 2025 or 2026 dependent on invitation from ACE. Culture Service is confident on return documentation. Museum in much stronger position than in 23/24 and work progresses to ensure long term sustainability and development with funding bids ahead of LGR.
| Improve quality of life | 2.3f | Delivery of £24.8m Long Eaton Town Deal programme, including West Park lighting scheme, Broad Street Bridge and waterside improvements | Resources | Planning | Tom Haddock | Amber | Only the Long Eaton High Street remaining in the design development and budget setting phase. This is currently running behind programme due to the estimated forecast received from the Design and Build Contractor, Galliford Try, providing some significant budget challenges. Officers are working with Derbyshire County Council and the contractor to review the scope and then progress to an assured Full Business Case. The Stable Block remains in the construction phase having suffered several delays and further design issues being discovered. Galaxy Row - demolition works are progressing well on site and will be complete August 2025. The developer will then commence the ‘build’ phase in August with an aim to complete December 2026. Both bridge projects and the West Park Waterfront Project are being progressed, with the council expected to enter into contaracts for these projects during August 2025, with works to start on site during late autumn. | West Park Lighting Project substantially complete. Britania Mills Bridge, Broad Street Bridge and Waterfront both have obtained planning consent and are now in the detailed design stage with early contractor involvement. Galaxy Row - Procurement of Development Partner ongoing. West Park Lighting Project complete. West Park Events Field Car Park Complete. Britania Mills Bridge now progressing through Full Business Case Stage, Broad Street Bridge and Waterfront both have obtained planning consent and are now in the detailed design stage with early contractor involvement. Galaxy Row - Preferred Development Partner identified and Legal Contracts being drafted. Long Eaton High Street 2D design completed and public consultation exercise commence on 06 Jan 2025. Britania Mills Bridge Full Business Case Completed and Assured with Sign off by Council S.151 Officer. Full Business Case being drafted for West Park Waterfront and Broad Street Bridge Projects. Detailed Design for Long Eaton High Street. Galaxy Row - Legal drafting of Development Agreement Progressing in consultation with Council's preferred Development Partner, MyPad 2020, with agreement reached for Developer to undertake all required demolition and site clearance works. West Park Lighting Project complete. West Park Events Field Car Park Complete.

## Priority 3
Sustainable Environment Actions
Reporting period
Q1 2024-25
Summary All actions have commenced and are progressing to target, with two now completed. Previous updates are provided for reference. As the plan progresses, we will provide a summary of all previous updates, in addition to the latest position.
[5 empty] | Red | 0 | 0%
Home |  |  |  |  | Amber | 0 | 0%
[5 empty] | Green | 8 | 80%
Summary |  |  |  |  | Completed | 2 | 20%
Delivery Plan |  |  |  |  | Not started | 0
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Performance Indicators | Objective | Corporate Strat Ref | Action | Directorate | Service | Owner | RAG | Latest update | Previous updates
| Deliver and respond to climate change | 3.1a | Publish an Annual Climate Change Statement as well as engage and raise awareness of actions residents and partners can take in response to climate change | Environmental & Community Services | Regulatory & Housing Services | Nick Thurstan | Green | Work is in progress on the Annual Climate Change statement for 2024/25, to be submitted to November Council Executive. | The council's first annual climate change statement for 2022-23 was approved by the Council Executive on 24 February 2024. The annual statement for 2023-24 is due to be considered by the Council Executive on 25 February 2025. The Annual Climate Change Statement for 2023/24 was approved by the Councill Executive on 25 February 2025. The council's web site now has new climate change pages that mirror the key priorities in the Climate Change Strategy 2025-30 and include general information on how busiensses and residents can take action to reduce greenhouse gas emissions and adapt to a changing climate. Further business and community engagement will be undertaken during the coming year.
Financial Summary | Deliver and respond to climate change | 3.1b | Establish and publish a new corporate Climate Change Strategy and action plan | Environmental & Community Services | Regulatory & Housing Services | Nick Thurstan | Completed | The Climate Change Strategy 2025-30 was approved by Council on 6 March 2025 and has since been published on the council's new web site. | Key headline content for the strategy was agreed by the Climate Change Action Working Group on 11/9/2024. Draft strategy completed whcih is due to be considered by teh Council Executive on 25 February 2025.
| Deliver and respond to climate change | 3.1c | Pursue opportunities for investment (when available/externally secured) to support decarbonisation of the council’s operations, property and fleet assets | Environmental & Community Services | Operational Services | Dave Bramwell | Green | Fleet Decarbonisation: the full fleet review will be complete by 11 September. A transition plan will be developed from this. Buildings decarbonisation: on pause at this time, a business case for proceeding will be developed. The coming Retrofit Strategy should help with this. Energy generation: we have secured funding from Midlands Net Zero Hub for a geotechnical survey at land adjacent to Merlin Way depot for a solar array. Our local area energy plan stakeholder engagement is also under way (from 31/07/2025) - there is expected to be funding opportunities here and also opportunities for partnership funding. | Fleet review underway, including consideration of alternative fuel use. Ongoing schemes for decarbonisation works at the leisure centres following successfully securing £2.8m of external grant funding. Property and Estates to liaise with the Climate Change Officer regarding further schemes and external grant opportunities.
Risks | Deliver and respond to climate change | 3.1d | Facilitate the promotion and retrofitting of energy efficiency measures and low carbon technologies in eligible residential properties | Environmental & Community Services | Regulatory & Housing Services | Nick Thurstan | Green | Following Housing's delivery and completion of last year’s retrofit schemes (HUG2, UKSPF and the Devolution Retrofit Fund) the next wave of government funded domestic energy efficiency grants, Warm Homes: Local Grant (WH:LG) launched at the start of April. Delivery of the WH:LG programme is anticipated to start soon with preparatory work underway; this will be followed by on-site delivery of energy efficiency measures later in the year following procurement of a delivery partner. In May, the Housing Service participated in D2N2’s Local Area Retrofit Accelerator workshops to help formulate a regional retrofit strategy. | Dedicated officer in place (fixed-term) to lead programmes with Home Upgrade Grant Phase 2 (HUG2), UK Shared Prosperity Funding (UKSPF) and Devolution funding projects all being delivered. 32 households have benefitted to date with a further 8 anticipated to benefit by year end. Solar panels and wall insulation are the most common measures. Service about to express an interest in the new national funding for energy efficiency measures, Warm Homes: Local Grant (WH:LG) from April 2025. By the end of 2024, 34 households had received energy efficiency measures and low carbon heating technology with a maximum 12 more installations planned by financial year end. An expression of interest was submitted to the Midlands Net Zero Hub (part of Nottingham City Council) for Erewash to continue to work in partnership with the consortium and be part of the application for the forthcoming Warm Homes: Local Grant programme starting in April. Project Coordinator (Home Retrofit) post made permanent on 20 March and postholder confirmed in post. By the end of March 2024, all three programmes (HUG2, UKSPF and Devolution) had been delivered with 43 households benefitting from 45 measures. Two voluntary groups also benefitted from the innovative Charity Buildings programme which supported local charities through a reduction in energy costs. Erewash’s allocation for the Warm Homes: Local Grant scheme is £819,500 across a three-year programme to March 2028, with the possibility for more funding (and two additional years) following the next HM Treasury Spending Review. Analysis of carbon emissions reductions is incomplete but data from the Shared Prosperity Fund estimates 27.3 tonnes of carbon dioxide is the reduction resulting from the combined energy efficiency and renewable energy measures installed - the equivalent of flying from London to Sydney nine times.
| Implement new waste management | 3.2a | Implement new statutory food waste household collections and promote participation | Environmental & Community Services | Operational Services | Dave Bramwell | Green | The deadline is April 2026 for household food waste collections with confirmation awaited on national revenue funding. (Transitional funding has been allocated and awaiting updates on ongoing deliver funding). Appropriate refuse collection vehicles ordered and awaiting delivery utlising the national capital funding allocation. Work continues to develop the plans to implement the new service. The commercial waste collection service started on 1st April 2025 and EBC are working with local schools initially. Internal processes have been implemented as of 1st April to separate and collect food waste at each of our main buildings. | The deadline is April 2026 for household food waste collections with confirmation awaited on national revenue funding. Appropriate refuse collection vehicles ordered and awaiting delivery utlising the national capital funding allocation. Work continues to develop the plans to implement the new service. Consideration is also being given to the implications for the commercial waste collection service which is subject to different deadlines.
| Implement new waste management | 3.2b | Encourage residents to produce less waste and recycle more | Environmental & Community Services | Operational Services | Dave Bramwell | Green | New recycling contract in place. Feedback from provider monitored, with regular meetings, which will assist the council to deliver targeted campaigns via social media and press releases, where required. | New recycling contract in place. Feedback from provider monitored, with regular meetings, which will assist the council to deliver targeted campaigns via social media and press releases, where required.
| Look after the borough’s green spaces | 3.2c | Implement rewilding of the borough | Environmental & Community Services | Operational Services | Dave Bramwell | Green | Following engagement and feedback, some in-year changes and amendments to schedules have been made to the rewilding scheme. In agreement with members, minor adjustments have been made to the scheme and renamed the program "Land Management". Further promotions on all media including links with young people/schools/friends of groups. | Previous rewilding plan implemented successfully. Following engagement and feedback, some in-year changes and amendments to schedules have been made. Discussions in place with members to finalise future modifications to the scheme and to build on the community engagement (eg links with young people/schools/friends of groups).
| Look after the borough’s green spaces | 3.3a | Establish the new Pewit Coronation Meadows local nature reserve | Environmental & Community Services | Operational Services | Dave Bramwell | Completed | All capital works on site completed. | Work on site has commenced. So far we have installed 3 footpaths, 3 butterfly banks, litter bins and seating. Ongoing works to achieve local nature reserve status. Tree planting commenced and due to be completed in January 2025 with mosaic habitat creation being planned for spring 2025
| Look after the borough’s green spaces | 3.3b | Maintain the high standards of West Park and Victoria Park for community use | Environmental & Community Services | Operational Services | Dave Bramwell | Green | Ongoing maintenance schedules at both sites as agreed with members, with a view to continuing the provision of high quality green spaces. | Ongoing maintenance schedules at both sites as agreed with members, with a view to continuing the provision of high quality green spaces.
| Look after the borough’s green spaces | 3.3c | Continue the provision of sports pitches and play parks across the borough | Environmental & Community Services | Operational Services | Dave Bramwell | Green | Ongoing maintenance schedules at all sites as agreed with members, with a view to continuing the provision of high quality sports pitches across the borough. New capital funding has been allocated over the next 2 to 3 years for full refurbishment of 5 play areas. Highest priority site is Wash Meadows, Ilkeston which is due for completion March 2026. | Junior football pitch added at West Park. Maintenance of all other relevant sites continues.

## Priority 4
A Modern Council Actions
Reporting period
Q1 2024-25
Summary All commenced actions are on target, with three already completed. There is a new action, for Local Government Reorganisation, which replaces the completed Productivity Plan action. Previous updates are provided for reference. As the plan progresses, we will provide a summary of all previous updates, in addition to the latest position.
[5 empty] | Red | 0 | 0%
Home |  |  |  |  | Amber | 0 | 0%
[5 empty] | Green | 8 | 72.73%
Summary |  |  |  |  | Completed | 3 | 27.27%
Delivery Plan |  |  |  |  | Not started | 2
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Performance Indicators | Objective | Corporate Strat Ref | Action | Directorate | Service | Owner | RAG | Latest update | Previous updates
| Make best use of resources | 4.1a | Review of the Council Constitution to enable more efficient ways of working | Resources | Law & Governance | Danielle Hughes | Green | We continue to review the Constitution with a view to prioritising the next updates. | The Financial Regulations have been reviewed and are due to be considered by Full Council on 31/10/2024. The Contract Procedure Rules are also being reviewed and will come to Full Council in due course. The Financial Regulations were approved by Full Council on 31/10/24. The Contract Procedure Rules will be going to General Purposes Committee for comments in January (2025), followed by Full Council in March. The Contract Procedure Rules were approved by Council In January, to add to the Financial Regulations being approved earlier in the year.
Financial Summary | Make best use of resources | 4.1b | Introduce a new workforce development strategy aimed at developing a suitably skilled, motivated and engaged workforce | Resources | Human Resources | Jo Watts | Green | New Learning and Development Officer started on 31 March 2025. Progress is being made on delivering key elements including new flexi time scheme. | This was presented to and approved by the Executive in October. The council is investing £80,000 into staff training and recruiting a Learning and Development officer to support improvements in front line departments. Progress is being made on delivering key elements including new e-learning platform rolled out, new intranet in place and new staff benefits scheme introduced.
| Make best use of resources | 4.1c | Enhance Member and staff training and development programme | Resources | Law & Governance | Danielle Hughes/Jo Watts | Green | The Learning and Development Officer is developing a corporate training programme for all staff and working with Elections, Democratic and Civic Services to develop a Member Development Programme. A new leadership development programme is in development with a view to upskilling aspiring and existing managers to be effective future leaders. Other training programmes are in development to address identified training needs such as improving HR policy application and Finance System user confidence. The new e-learning platform - SkillGate - is operational and access to mandatory training programmes will be made available to members soon. The council has achieved 100% completion rate for all mandatory courses allocated to staff. | A member survey is currently in circulation (closing date October 24). This will help inform the draft Member Development Programme. The new E-Learning platform will be live in the new year for staff and Members. Following the member survey, we have completed a first draft Member Development Programme. The new E-learning platform was launched in December 2024. New Learning and Development Officer started on 31 March 2025. Corporate Learning and Development plan in development following discussions with Heads of Service. SkillGate e-learning mandatory courses released and allocated to staff with 50% completion rate at end of Q4. Member Development Programme in development in Elections, Democratic and Civic Services.
Risks | Make best use of resources | 4.1d | Develop and implement new Property Asset Management Plan including the disposal of surplus council assets | Environmental & Community Services | Property & Estates | Tom Haddock | Green | Property & Leisure Services have porgressed several asset disposals by way of lettings of surplus assets such as former public conveniences. Progress has been made on the car park review to develop proposals for potentailly surplus assets subject to further recommendations and approvals | Property Asset Management Plan approved by the Council Executive on 01 October 2024, subject to call in. The council is continuing with its asset disposal plan and with improvements to current assets such as leisure centres using government grants. Property Asset Management Plan (PAMP) approved by the Council Executive on 01 October 2024. Following the Devolution White Paper published by the Government on 16 December 2024, which included the proposals for government’s intended reorganization of local government, the council has been carefully considering the potential impact. Owing to the high level of uncertainly over the future lifespan of council assets, including the unknown requirement of any new unitary authority, it has been determined not to proceed with the next stage of the Town Hall Options Appraisal at this time.
| Make best use of resources | 4.1e | Develop a modern approach to communication with an emphasis on refreshing the approach to consultation and engagement and consultation | Environmental & Community Services | Communications & Culture | Stewart Millar | Green | New consultation and engagement platform, Let's Talk Erewash launched in January 2025, with the Budget Survey. Further awareness events developed and delivered across staff, whilst additional staff training and familiarisation continued during Q4. Briefing Session planned in very early Q1 2025/26 to Senior Management Team to further share the opportunities that the new platform can bring. The communications e-newsletters continue to build audience with the public e-newsletter achieving 7,000 subscriptions and a 76% open rate which is way above the industry average. The staff e-newsletter has been well received and a recent issue on cybercrime achieved an 80% plus open rate. The LGA carried out an independent communications health check in March and the newly designed corporate website was launched in early April. | A new monthly e-newsletter for residents was launched in September, backed by a successful marketing communications programme – subscription levels of 5k plus have been achieved over a short period and an open rate of 74% registered for the October newsletter, well above the average of 40% for other public sector organisations. A staff e-newsletter has also been developed and was launched in November. New Corporate Style Guide completed - the style guide moves away from traditional branding elements and embraces a more modern and accesible aesthetic. It aims to Enhance the council's public image by presenting a consistent and professional image across all communication channels; Improve brand recognition by establishing a clear and memorable identity for the council; Improve communication effectiveness by ensuring all communications are clear, concise, and easy to understand for our residents; Streamline design processes providing clear guidelines for staff and external partners on the use of logos, colours, typography, and imagery. New online networks launched including public e-newsletter, staff e-newsletter, and new consultation platform, Engagement HQ. Staff training continues on the new public consultation and engagement platform, Let's Talk Erewash, which is expected to be launched in January 2025– this will help improve engagement, consultation, and resident participation.
| Ensure financial stability | 4.2a | Deliver planned savings in 2024/25 and a balanced budget in 2025/26 | Resources | Accountancy | Judy Fay | Completed | Balanced budget for 2025/26 set. Monitoring of savings achieved is reported quarterly to Council Executive. | Budget development in progress. Monitoring of savings achieved is reported quarterly to Council Executive.
| Ensure financial stability | 4.2b | Develop a ten-year capital programme setting out long term investment and maintenance plans | Resources | Accountancy | Judy Fay | Green | The long term capital programme is 90% complete. With the advent of Local Government Reorganisation, the Council will defer any further work for now. | The long term capital programme is 90% complete. With the advent of Local Government Reorganisation, the Council will defer any further work for now.
| Ensure financial stability | 4.2c | Develop Invest to Save Policy to provide a framework for investment | Resources | Accountancy | Judy Fay | Not started | This is no longer going to happen due to Local Government Reorganisation | Due to start in 2025/26. For now, any invest to save iniatives will be considered on a case by case basis.
| Ensure financial stability | 4.2d | Produce, with neighbouring councils, a proposal for Local Government Reorganisation in Derbyshire by November | Corporate | Corporate | CMT | Green | The eight Derbyshire district and borough councils, working with Derby City Council, continue to work together to develop proposals for local government reorganisation. A two-option joint interim proposal was submitted by the Government’s 21 March 2025 deadline (one northern unitary and one southern unitary with Amber Valley in the north in option A and Amber Valley in the south in option B). Working with the nine other councils, a public consultation was launched on these two options with a third option of part of Amber Valley being in the north and part in the south, to run from 30 June to 10 August, ahead of the final proposal which needs to be submitted to government by the 28 November 2025. Working groups across key functions of the authorities have commenced, to ensure all of the information necessary is available for an evidenced based and robust final proposal. | New - Replaces Productivity Plan action (completed)
| Ensure financial stability | 4.2e | Respond to Government funding consultation and lobby for additional funding for Erewash | Resources | Accountancy | Judy Fay | Not started | The Council will respond to finance consultations as and when they are released. | Spending Review submission completed by the Director of Resources based on the Productivity Plan produced and agreed by Members.
| Utilise technology to transform service delivery | 4.3a | Develop an ICT and digital strategy (including assessment of investment required) to enable more efficient working and protect the council from cyber risk | Resources | ICT | Andy Nix | Completed | The ICT and Digital Strategy was approved in October 2024. With the investment made the Council is in the process of delivering a number of key projects including a new website (launched in April), new intranet (launched in January), improvements in the Erewash Account (planned to go live in Quarter 3 2025/26) and a new Planning and Building Control system that will be better for customers. | ICT Strategy presented to and approved by Council Executive on 1st October 2024. The council is investing over £300,000 in various projects including a new website, improvements in the Erewash Account and a new Planning and Building Control system that will be better for customers. IT Strategy published
| Utilise technology to transform service delivery | 4.3b | Implement new waste management system | Environmental & Community Services | ICT | Andy Nix | Completed | The new system was implemented successfully. The system has been used to implement Garden Waste subscriptions and improve operational efficiency in the way missed bins are dealt with. | System implemented successfully. The system has been used to implement Garden Waste subscriptions and improve operational efficiency in the way missed bins are dealt with.
| Utilise technology to transform service delivery | 4.3c | Review customer portal and options for increasing ability to transact online to support channel shift | Resources | ICT | Andy Nix | Green | In progress. A significant project is runningwithin Revs and Bens allowing customers to view their acocunt details online and to complete forms that enter straight into the back office system. We are developing a new plan for the delivery of a customer portal. | This is in progress. We have identified areas where there are options for increasing ability to do things online e.g. complaints, Freedom of Information requests, road closures. Changes to the Customer Portal will happen after the new website has been implemented.

## Performance Indicators
Key Performance Indicator library
Reporting period
Q1 2024-25 | To support the new Corporate Strategy, and in addition to the Delivery Plan, we have introduced a new suite of Key Performance Indicators (KPIs). As with the Deliver Plan Actions, these are split by Corporate Priority: 1. Economy and Regeneration 2. Supporting Communities 3. Sustainable Environment 4. A Modern Council Performance is reported quarterly, with the exception of indicators that those that are measured at year-end. For those with an outturn, a 'Red, Amber, Green' rating, to show whether the indicator has met target. A summary table for progress against each priority is available on each priority page, with overall progress against the plan noted on the 'Summary' page of this dashboard.
Home
Summary
Delivery Plan
Performance Indicators
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Financial Summary
Risks

## KPI 1
Economy and Regeneration Indicators
Reporting period
Q1 2024-25
Summary All reported actions are green.
Home | [5 empty] | Red | 0 | 0%
[6 empty] | Amber | 0 | 0%
Summary | [5 empty] | Green | 5 | 100%
Delivery Plan | [5 empty] | Not started/annual | 0
Performance Indicators
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Financial Summary | Indicator Ref | sort | Indicator | Directorate | Service | Owner | Target | Frequency | Quarter 1 position | RAG | Commentary
| ER - 1 | -1 | Processing of major planning applications within timescales | Resources | Planning Development | Steve Birkinshaw | 90.3% | Quarterly | 100% | Green | 3 out of 3 decisions in time.
Risks | ER - 2 | -2 | Processing of minor planning applications within timescales | Resources | Planning Development | Steve Birkinshaw | 88.7% | Quarterly | 89% | Green | 8 out of 9 decisions in time.
| ER - 3 | -3 | Processing of other planning applications within timescales | Resources | Planning Development | Steve Birkinshaw | 88.7% | Quarterly | 97% | Green | 71 out of 73 decisions in time
| ER - 4 | -4 | Percentage of major planning applications overturned on appeal | Resources | Planning Development | Steve Birkinshaw | 4% | Quarterly | 0% | Green | 0 decisions overturned at appeal
| ER - 5 | -5 | Percentage of non-major planning applications overturned on appeal | Resources | Planning Development | Steve Birkinshaw | 1% | Quarterly | 0% | Green | 0 decisions overturned at appeal

## KPI 2
Supporting Communities Indicators
Reporting period
Q1 2024-25
Summary Two red indicators, for benefits processing times.
Home | [5 empty] | Red | 2 | 15.38%
[6 empty] | Amber | 0 | 0%
Summary | [5 empty] | Green | 11 | 84.62%
Delivery Plan | [5 empty] | For info only | 1
Performance Indicators
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Financial Summary | Indicator Ref | sort | Indicator | Directorate | Service | Owner | Target | Frequency | Quarter 1 position | RAG | Commentary
| SC - 1 | -1 | The percentage of dangerous structures reported to the building control service that were responded to within 24 hours | Environmental & Community Services | Building Control | Nick Thurstan | 95% | Quarterly | 100% | Green | 22 dangerous structures reported in Q1, all visited within 24 hours.
Risks | SC - 2 | -2 | Number of residents participating in council-run or partnered health and wellbeing programmes | Environmental & Community Services | Communications & Culture | Stewart Millar | 800 | Quarterly | 1178 | Green | High numbers in Q1 due to 600 throughout walking month.
| SC - 3 | -3 | Number of visitors to Erewash Museum | Environmental & Community Services | Communications & Culture | Stewart Millar | 4000 | Quarterly | 4318 | Green | 26.85% increase on the same period in 2024, despite one week in June being closed for a refurb. April saw a significant increase in visitor figures, which more than made up for a drop in June.
| SC - 4 | -4 | Customer complaints responded to within timescales | Environmental & Community Services | Communications & Culture | Stewart Millar | 95% | Quarterly | 100% | Green | 4 acknowledgements were late but all of the responses from services were within 10 days of the date the acknolwedgement should have been issued
| SC - 5 | -5 | Number of organisations supported by Fast Fund Community Grants | Environmental & Community Services | Communications & Culture | Stewart Millar | For info | Quarterly | - | - | No grants awarded in Q1. New scheme live from July 25
| SC - 6 | -6 | Percentage of food safety inspections due during the year completed | Environmental & Community Services | Environmental Health | Nick Thurstan | 25% | Quarterly | 26% | Green | All planned inspections completed
| SC - 7 | -7 | Percentage of animal welfare premises inspections due during the year completed | Environmental & Community Services | Environmental Health | Nick Thurstan | 25% | Quarterly | 27% | Green | All planned inspections completed
| SC - 8 | -8 | Percentage of homelessness prevention cases received during the financial year closed with a successful outcome. | Environmental & Community Services | Homelessness | Nick Thurstan | 50% | Quarterly | 77% | Green | The higher than expected % of successful preventions this quarter is as a result of proactive prevention work and continued work with social housing providers to move people on in a timely manner.
| SC - 9 | -9 | Percentage of homelessness relief cases received during the financial year closed with a successful outcome | Environmental & Community Services | Homelessness | Nick Thurstan | 30% | Quarterly | 73% | Green | As with homelessness prevention, proactive move-on work and continued work with social housing providers to move people on in a timely manner has resulted in a much higher success.
| SC - 10 | -10 | Percentage of licensed premises compliant with licensing requirements within 21 days following initial intervention by the council | Environmental & Community Services | Licensing | Nick Thurstan | 100% | Quarterly | 100% | Green | Intervention with 22 premises, only one found to be non- compliant with licensing requirements. Issues rectified.
| SC - 11 | -11 | Percentage of licence applications under the Licensing Act determined within 5 working days (following consultation except where the application is referred to a Licensing and Public Protection Panel) | Environmental & Community Services | Licensing | Nick Thurstan | 100% | Quarterly | 100% | Green | 51 licence applications received and all determined within 5 days of the consultation.
| SC - 12 | -12 | Percentage of homes made safe to live in where a serious hazard has been identified on inspection | Environmental & Community Services | Private sector housing | Nick Thurstan | 100% | Quarterly | 100% | Green | 4 Category 1 Hazards removed/reduced within 4 rented properties and 7 high Category 2 Hazards removed/reduced within 5 rented properties in Q1, following the Council's intervention.
| SC - 13 | -13 | Revs and bens - time (days) taken to process new Housing Benefit claims | Resources | Revenues & Benefits | Lisa Black | 19 | Quarterly | 23.6 | Red | Year-to-date performance stands at 23.6 days, which is 4.6 days above the annual target. Performance in Quarter 1 was adversely affected by the typical post-year-end workload pressures, further exacerbated by long-term staff sickness. In response, the service has proactively increased capacity by utilising its resilience contract and engaging agency staff to help stabilise performance levels.
| SC - 14 | -14 | Revs and Bens Time (days) taken to process Housing Benefit change of circumstances | Resources | Revenues & Benefits | Lisa Black | 9 | Quarterly | 14.4 | Red | Year-to-date performance stands at 14.4 days, which is 5.4 days above the annual target. The service processed 28,078 changes in the period. Performance in Quarter 1 was adversely affected by the typical post-year-end workload pressures, further exacerbated by long-term staff sickness. In response, the service has proactively increased capacity by utilising its resilience contract and engaging agency staff to help stabilise performance levels.

## KPI 3
Sustainable Environment Indicators
Reporting period
Q1 2024-25
Summary Two red and two amber indicators for Waste and Recycling. The ones for household waste are always reported one quarter in arrears as the data is not available until submitted to government, usually after the reporting period for the relevant quarter.
Home | [5 empty] | Red | 2 | 40%
[6 empty] | Amber | 2 | 40%
Summary | [5 empty] | Green | 1 | 20%
Delivery Plan | [5 empty] | Not started/annual | 1
Performance Indicators
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Financial Summary | Indicator Ref | sort | Indicator | Directorate | Service | Owner | Target | Frequency | Quarter 1 position | RAG | Commentary
| SE - 1 | -1 | Percentage of permits for polluting industrial processes due during the year completed | Environmental & Community Services | Environmental Protection | Nick Thurstan | 90% | Quarterly | - | Not started | Permit inspections are not due until quarter 4.
Risks | SE - 2 | -2 | Percentage of Environmental Protection first responses to service requests completed within 3 working days | Environmental & Community Services | Environmental Protection | Nick Thurstan | 90% | Quarterly | 99% | Green
| SE - 3 | -3 | Residual waste per household (kg) | Environmental & Community Services | Waste and Recycling | Dave Bramwell | No more than 486 | Quarterly | 515.5 | Amber | Outturn is for Quarter 4 2024-25, reported one quarter in arrears and is 6% over target. This indicator is measured cumulatively, with a profiled target throughout the year.
| SE - 4 | -4 | Household waste recycling/composting rate | Environmental & Community Services | Waste and Recycling | Dave Bramwell | 42% | Quarterly | 35.7% | Red | Outturn is for Quarter 4 2024-25, reported one quarter in arrears. This indicator is measured cumulatively. The recycling/composting rate has been affected by lower tonnages of dry recycling collected from households, higher rates of contamination under the new recycling contract, reduced tonnage of garden waste collected under the new chargeable garden waste service and an increase in tonnage of residual waste collected.
| SE - 5 | -5 | Recycling contamination rate | Environmental & Community Services | Waste and Recycling | Dave Bramwell | No more than 10.5% | Quarterly | 16.16% | Red | Outturn is for Quarter 4 2024-25, reported one quarter in arrears. This indicator is measured cumulatively.
| SE - 6 | -6 | Number of missed bins per 100k collections | Environmental & Community Services | Waste and Recycling | Dave Bramwell | No more than 105 | Quarterly | 107.26 | Amber | Outturn is 2% over target. This indicator is measured cumulatively.

## KPI 4
A Modern Council Indicators
Reporting period
Q1 2024-25
Summary One red indicator. Details are below but it is subject to minor variances that can cause it to miss target.
Home | [5 empty] | Red | 1 | 7.143%
[6 empty] | Amber | 2 | 14.29%
Summary | [5 empty] | Green | 11 | 78.57%
Delivery Plan | [5 empty] | Not started/annual | 0
Performance Indicators
1. Economy and Regeneration
2. Supporting Communities
3. Sustainable Environment
4. A Modern Council
Financial Summary | Indicator Ref | sort | Indicator | Directorate | Service | Owner | Target | Frequency | Quarter 1 position | RAG | Commentary
| AMC - 1 | -1 | Post vacancy rate | Resources | Human Resources | Jo Watts | Not more than 12% | Quarterly | 16.6% | Red | In common with other councils, recruitment and retention continues to be a challenge. There is no one specific cause and the council is trying a number of different approaches to address this issue.Outturn has improved, slightly, on year-end (17%)
Risks | AMC - 2 | -2 | Number of data breaches referred to ICO | Resources | Law & Governance | Danielle Hughes | 0 | Quarterly | 0 | Green | There were 4 confirmed breaches in the quarter; none of them were considered enough of a risk to report to the ICO.
| AMC - 3 | -3 | Percentage of FOI and EIR requests processed within 20 working days | Resources | Law & Governance | Danielle Hughes | 95% | Quarterly | 98.3% | Green | There were 432 requests in the quarter (191 FOI, 241 EIR). This is up 18% on Q1 last year (366).
| AMC -4 | -4 | Percentage of Subject Access Requests processed within 1 month | Resources | Law & Governance | Danielle Hughes | 95% | Quarterly | 100% | Green | 12 SARs processed in quarter 1, all within 1 month
| AMC - 5 | -5 | Percentage of agendas published 5 working days before meetings | Resources | Law & Governance | Danielle Hughes | 95% | Quarterly | 100% | Green | 15 agendas were published in Q1 of 2025/26. 2 of these were for Licensing & Public Protection panels, that were called at 48 hour notice. These have been discounted from the calculation.
| AMC - 6 | -6 | Percentage of minutes published 10 working days following meetings | Resources | Law & Governance | Danielle Hughes | 95% | Quarterly | 100% | Green | 15 sets of minutes were published in Q1 of 2025/26, all within 10 working days following meetings.
| AMC - 7 | -7 | Land charges requests processed within 10 working days | Resources | Law & Governance | Danielle Hughes | 95% | Quarterly | 100% | Green | There were 666 Land Charges requests processed in the year to date, all within the response target. The average response time was 6.65 working days
| AMC - 8 | -8 | Business Rates Collection rates (NNDR) - in year | Resources | Revenues & Benefits | Lisa Black | 24.25% | Quarterly | 25.45% | Green | In year collection is on track. The service has collected £6,946k against a profiled target if £6,618k, some £328k up.
| AMC - 9 | -9 | Council Tax Collection rates - in year | Resources | Revenues & Benefits | Lisa Black | 28.1% | Quarterly | 27.96% | Amber | In year collection is marginally behind the profiled target at the end of the quarter. The service has collected £22,262k against a profiled target of £22,375k, some £113k behind the profile. In June the first court of the recovery year took place and we expect the ongoing recovery activities to see continuous improvement throughout the year.
| AMC - 11 | -11 | Average phone call wait time for the Contact Centre (minutes) | Environmental & Community Services | Communications & Culture | Stewart Millar | <6 mins | Quarterly | 5 mins 10 | Green
| AMC - 12 | -12 | Balanced budget for next 2 years | Resources | Accountancy | Judy Fay | Yes | Quarterly | Yes | Green | Balanced budget set for 2025/26; 2026/27 budget not due until quarter 4.
| AMC - 13 | -13 | Reserves projected to be of minimum for next 2 years | Resources | Accountancy | Judy Fay | Yes | Quarterly | Yes | Green | Based on the current MTFP, this is forecast to be achieved
| AMC - 14 | -14 | Statement of accounts published by May statutory deadline | Resources | Accountancy | Judy Fay | Yes | Quarterly | 96.6 | Green | 2024/25 Statement of Accounts published by 30 June deadline
| AMC - 15 | -15 | Percentage of invoices paid on time | Resources | Accountancy | Lisa Black | 95% | Quarterly | 94.5% | Amber | The service is on track to achieve a 95% outturn in 25/26. It has reviewed processes to check for "blockages" and is in direct conversation with service areas to help ensure that Purchase orders are raised to match invoices to aid spee of payment.

## Financial
Reporting period | Financial Summary
Q1 2024-25 | The Council's performance against its budget is reported quarterly to the Council Executive and to Scrutiny. More information about how we are doing can be found there. We have listed below, for information, a range of financial indicators – some of which are outside the control of the Council
Home
Summary
|  | Indicator ref | Indicator | Directorate | Service | Owner | Target | Quarter 4 position | RAG | Comments
Delivery Programme |  | FS1 | Total core spending power per dwelling | Resources | Accountancy | Judy Fay | For info | - | For info | The core spending power is extracted from the local government financial settlement which is due in the Autumn.
|  | FS2 | Total debt as percentage of core spending power | Resources | Accountancy | Judy Fay | 0 | 0% | Green | The council has zero long term borrowing
Performance Indicators |  | FS3 | Non-ringfenced reserves as percentage of net revenue expenditure | Resources | Accountancy | Judy Fay | For info | - | Annual | The core spending power is extracted from the local government financial settlement which is due in the Autumn.
|  | FS4 | Council tax revenue per dwelling | Resources | Revenues & Benefits | Lisa Black | For info | 141.31 | For info | Figure based on the local government finance settlement
Financial Summary |  | FS5 | Level of band D council tax rates | Resources | Revenues & Benefits | Lisa Black | For info | 213.83 | For info | This is the council tax for Erewash only, excludes police, fire etc.
|  | FS6 | Debt servicing as percentage of core spending power | Resources | Accountancy | Judy Fay | For info | Yes | Green | Council has zero long term borrowing
Risks |  | FS7 | Balanced budget for current year | Resources | Accountancy | Judy Fay | For info | Yes | For info | Balanced budget set for 2024/25
|  | FS8 | Gross external debt | Resources | Accountancy | Judy Fay | Yes | 0% | Green | Council has zero long term borrowing
|  | FS9 | Auditor approved accounts | Resources | Accountancy | Judy Fay | For info | Not yet due | For info | 2024/25 Accounts backstop date for the accounts to be discalimed is 27 February 2026. Audit planned to commence from Sep 25.

## Risks
Risks
Reporting period
The Strategic Risk Register contains 9 live strategic risks. Risk 4 (Long Eaton Town Board) has seen an increase in its residual risk due to current cost forecasts, which are being reviewed. The remaining risks all remain stable with ongoing management actions and controls in place. For more information, please see the September 2024 Audit Committee Strategic Risk Register at the link below.
Q1 2024-25
Home
Summary
Delivery Plan
Performance Indicators
Financial Summary |  |  |  | https://moderngov.erewash.gov.uk/ieListDocuments.aspx?CId=285&MId=2448
Risks |  | Risk | Description | Date added | Inherent risk score | Residual risk score | Latest movement | Latest update
|  | Risk ID 1 – Key priorities delivery | There is a risk we cannot deliver key/new priorities due to a lack of resources caused by retention/recruitment issues, budget or too big a corporate workload (including additional requirements from Government). | 2023-05-01 | 20 | 12 | çè | No overall change to risk profile. Updated comments regarding local government reorganisation proposals and Food Waste service funding.
|  | Risk ID 2 – Financial stability | There is a risk that the Council is not financially stable in the medium term (as evidenced by the gap in MTFF) due to uncertain future government funding. | 2019-06-01 | 25 | 20 | çè | No overall change to risk profile. Updated comments regarding budgets.
|  | Risk ID 3 – Housing land supply | Failure to demonstrate adequate housing land supply resulting in various impacts - a shortfall each year in property available for sale, house price inflation, local residents leaving the Borough or new people not moving in and loss of council tax base of £225,000 per year. | 2016-07-01 | 15 | 12 | çè | No change to risk profile – update to action section.
|  | Risk ID 4 – Long Eaton Town Board | The Town Board not able to deliver on one or more of its key projects resulting in failure to meet objectives, financial loss, reputational damage and frustration for residents. Risk includes construction cost inflation, council capacity to develop multiple projects, contractor administration risk, delays in design agreements, funding restricted to committed costs and completion deadline. | 2022-03-01 | 16 | 9 | é | Residual risk has been increased to reflect increased significant over-budget forecasts of the High Street project. The extent of financial risk exposure is dependent upon efficiency savings vs risk allocation of the High Street project. Updates made to regarding progress on various projects including business case completion.
|  | Risk ID 5 – ICT infrastructure | Lack of appropriate ICT/digital infrastructure undermines Council’s ability to deliver on its priorities and/or creates inefficiencies. | 2023-03-01 | - | - |  | Closed. It is considered that with the existing structure, controls, new ICT Strategy now in place and intranet and website developments underway this is no longer a strategic risk and is therefore closed as of January 2025.
|  | Risk ID 6 – Business Continuity | Failure to deliver key services should a significant business interruption occur. | 2023-05-01 | 16 | 9 | çè | No change to risk profile. A business continuity exercise took place with members of the management team in April 2025 to test the Council’s response to a cyber-attack.
|  | Risk ID 7 – GDPR compliance | Information Governance / GDPR Risk: There is a risk that the Council suffers a data protection breach arising from poor processes and controls, accidental or intentional actions including cyber attack, leading to potential harm to individuals, employees and members, legal action, financial penalties from ICO and reputational damage. | 2023-12-01 | 20 | 6 | çè | Jul 25 - No change to risk profile. Mandatory training for all staff and members launched in H1 2025, 95% completion by 1st July. Amended legislation identified and key officers received training. Controls embedded via policies, procedures and training.
|  | Risk ID 8 – Temporary Accommodation | There is a risk of significant overspend on supported housing and temporary accommodation, in order for the Council to deliver its duty on homelessness under the Housing Act 1996 and manage its duty around accommodation of families with children/pregnant women. | 2023-12-01 | 25 | 20 | çè | No change to risk profile. Actions and comments updated.
|  | Risk ID 9 – Cyber Attack | Cyber attack against the Council preventing delivery of critical services and/or breach or corruption of data. | 2024-09-01 | 12 | 12 | çè | No change to risk profile. Internal Audit review completed on Cyber Resilience which suggested some improvements, but gave a “Reasonable Assurance” opinion.
|  | Risk ID 10 - Government Devlotion | The impact of the Government’s Devolution White Paper creates some medium-term uncertainty which could have impacts on workforce (recruitment, retention and capacity), financial planning, and service delivery resulting in difficulties in delivering business as usual. | 2025-01-01 | - | 20 | çè | No change to risk profile. Actions and comments updated to reflect latest position of LGR work. Residual Risk score 20 (impact 4 x likelihood 5)

## Lookup (hidden)
Q2 2024-25 | 2024-09-30 | Q2 2024-25
Q3 2024-25 | 2024-12-31 | Q3 2024-25
Q4 2024-25 | 2025-03-31 | Q4 2024-25
Q1 2025-26 | 2025-06-30 | Q1 2025-26
Q2 2025-26 | 2025-09-30 | Q2 2025-26
Q3 2025-26 | 2025-12-31 | Q3 2025-26
Q4 2025-26 | 2026-03-31 | Q4 2025-26
Q1 2026-27 | 2026-06-30 | Q1 2026-27
Q2 2026-27 | 2026-09-30 | Q2 2026-27
Q3 2026-27 | 2026-12-31 | Q3 2026-27
Q4 2026-27 | 2027-03-31 | Q4 2026-27
Q1 2027-28 | 2027-06-30 | Q1 2027-28
Q2 2027-28 | 2027-09-30 | Q2 2027-28
Q3 2027-28 | 2027-12-31 | Q3 2027-28
Q4 2027-28 | 2028-03-31 | Q4 2027-28
Q1 2028-29 | 2028-06-30 | Q1 2028-29
Q2 2028-29 | 2028-09-30 | Q2 2028-29
Q3 2028-29 | 2028-12-31 | Q3 2028-29
Q4 2028-29 | 2029-03-31 | Q4 2028-29
Q1 2029-30 | 2029-06-30 | Q1 2029-30
Q2 2029-30 | 2029-09-30 | Q2 2029-30
Q3 2029-30 | 2029-12-31 | Q3 2029-30
Q4 2029-30 | 2030-03-31 | Q4 2029-30
Q1 2030-31 | 2030-06-30 | Q1 2030-31
Q2 2030-31 | 2030-09-30 | Q2 2030-31
Q3 2030-31 | 2030-12-31 | Q3 2030-31
Q4 2030-31 | 2031-03-31 | Q4 2030-31
Q1 2031-32 | 2031-06-30 | Q1 2031-32
Q2 2031-32 | 2031-09-30 | Q2 2031-32
Q3 2031-32 | 2031-12-31 | Q3 2031-32
Q4 2031-32 | 2032-03-31 | Q4 2031-32
Q1 2032-33 | 2032-06-30 | Q1 2032-33
Q2 2032-33 | 2032-09-30 | Q2 2032-33
Q3 2032-33 | 2032-12-31 | Q3 2032-33
Q4 2032-33 | 2033-03-31 | Q4 2032-33
Q1 2033-34 | 2033-06-30 | Q1 2033-34
Q2 2033-34 | 2033-09-30 | Q2 2033-34
Q3 2033-34 | 2033-12-31 | Q3 2033-34
Q4 2033-34 | 2034-03-31 | Q4 2033-34